## PACA PPM activities planning
3rd PACA PARTNERSHIP PLATFORM MEETING - DRAFT WORK PLAN
Activities Planning
Activities |  |  |  |  | Activities Planning
Output |  | Activities | Person(s) Responsible | status | 2014-01-01 | 2018-05-18 | 2018-06-18 | 2018-07-18 | 2018-08-18 | 2018-09-18 | 2018-10-18 | 2018-11-01
1 | PACA PPM Coordination Team | Identify meeting faciliators for the PPM | Amare | Done
Confirm meeting date - 2-4 October
|  |  | Steering Committee | Done
|  | Develop and Update PACA PPM draft work plan | Winta | Done
|  | Conduct conference call with Facilitators every 2 weeks | Amare, Liz, Winta and Mahlet | Scheduled
|  | Discuss and agree on frequency of communication/ conference calls with facilitation team | Winta and PCIO
|  | Develop detailed logistics plan (meeting halls, catering, A/V, etc.) | Winta, Mahlet and hotel
|  | Identify hotel and confirm availability | Winta, Mahlet and Procurement
|  | Work with procurement to identify and secure hotel | Procurement
2 | Meeting Materials and Content | Develop draft concept note and meeting programme | Winta, Amare, PICO team
|  | Identify key speakers, presenters, panelists etc… | Amare, Winta, PICO
|  | Programme circulated to SC / Annotated agenda | Amare
|  | Background materials/ documents selected ( | Amare, Martin, Liz, and Winta
|  | Invite and confirm participation of presenters, speakers etc.. | Winta and Peace
|  | Calls conducted with presenters and PPT collected | Winta, Peace and PICO
|  | Meeting documents sent to translation in all four AUC languages / September | Winta and Mahlet
|  | Prepare all meeting materials for printing | Amare, Winta and Mahlet
|  | Print all meeting documents for distribution | Mahlet and support
3 |  | Send announcement and updated concept note to PACA Community | Winta and Peace
|  | Develop criteria for supporting participants | Winta and Liz
| Invite Participants | Prepare and send draft invitee list for comment and input | Winta and Secretariat
|  | Review input and finalize invitee list | Winta and secretariat
|  | Prepare draft invitation letter for participants | Winta
|  | Review input, get invitation letters signed by COMREA and others (Chairperson) and send letters | Winta and Mahlet
|  | Draft and sent invitations | Winta and Amare
Dignitaries Management
|  | Confirm Participation | Winta and Mahlet
|  | Liaise with Relavant offices for protocol | AUC Protocol, Mahlet and Winta
|  | Confirm VIP areas in hotel | Mahlet and Winta
| Partners Management | Send invitations | Winta and Mahlet
|  | Confirmation of partners | Winta and Liz
|  | Confirm and conduct bilaterals with partners | Liz and Amare
4 | Participant Management | Create and Manage an (online) registration process | Peace and Peace
|  | Compile all confirmed registration list with departure and arrival dates | Mahlet
|  | Draft and issue logistics note to all participants | Mahlet
|  | Draft and issue Visa letters to all participants (Dakar may not need Visa) | Mahlet
|  | Book accommodation for all participants | Mahlet and Winta
|  | Arrange ground transportation from airport to hotel | Mahlet and Magatte
|  | Arrange ground transportation from hotel to Conference center | Mahlet and Magatte
|  | Provide travel arrangement for supported participants (Air tickets for particpants) | Mahlet and support
5 | AUC internal communication to service the PACA PPM | Draft and send memos for the relevant departments to service the PACA PPM: Finance, Conferences, Procurement, Travel Unit, and Communications | Winta and Mahlet
|  | Confirm PICO services with procurement | Winta and Mahlet
Mahlet
|  | Engage with AUC selected Events planner for all logistics | Mahlet and Magatte | ?
|  | Confirm catering and A/V arrangements | Winta and Mahlet
|  | Communications Unit: Media invitation and management | Ibrahim
|  | Required stationery for Secretariat and delegates | Mahlet and Winta
|  | Audiovisual equipment | Peace and Ibrahim
|  | Audiovisual technician contact | Peace
Handling of documents: ppts, speeches, background documents, etc during the meeting
|  | Room signage | Hotel and Mahlet
|  | Secretariat and other service rooms as required | Mahlet
|  | Registration desk/area at gate | Hotel and Ushers
|  | Registration desk within the conference complex | Hotel
|  | Accreditation tags | Winta and Mahlet
|  | Name badges (note that these are needed in addition to the above tags – which at AUC do not have names!) | Winta and Mahlet
|  | Branded items (banners, stationery) | Winta, Mahlet and Procurement
|  | Confirm interpreters and interpretation equipment | Mahlet
|  | Procure Materials for the Market place (flip charts, post-it, pins, booths etc…) | Winta and Mahlet
6 | Meeting Documentation Post Workshop | Meeting report drafted | PICO Team
|  | Communique drafted and sent for SC review | Ibrahim and Winta
|  | Communique finalized and sent to community | Amare
|  | Follow-up actions initiated | Secretariat