## Sheet1
Communication Activity Matrix for 3rd PACA PPM
Activity |  | Responsibility
1.0. Objective One- Facilitate the PPM organizational communication- Preparatory stage
1.1. Branding- (All branded materials in English and French)
| · Design of the 3rd PPM logo | Ibrahim and Peace
| · Production of banners: drop down banner, display banner, pull up banner. | Ibrahim and Mahlet
| · Announce the 3rd PPM with the banner on PACA Website, and shared with other popular platforms. | Peace and Ibrahim
1.2. Information and Knowledge Materials
| · Production of PACA Video | Ibrahim and Liz
| · Production of 3rd PPM /PACA branded jacket/folder for the packaging of PACA materials | Mahlet and Ibrahim
| · Printing of PACA Documents; 10 facts, policy briefs, flyers etc. | Mahlet, Ibrahim and Wezi
| · Acquisition of TV Screen for twitter thread | Mahlet
| · Printing of 3rd PPM program outline. | Mahlet
1.3. Organizational
| · Establishment of PACA organizers’ communication platform e.g. WhatsApp. | Peace and Wezi
| · Write draft speeches for the invited guest speakers | ?
1.4. Media Relations
| · Identify and invite media personnel for coverage (pilot country and Senegal) | Country officers and Ibrahim
| · Develop media brief on 3rd PPM | Ibrahim and Winta
| · Identify and hire professional video recorder and one cameraman | Magatte and Ibrahim
2. Objective 2. During the Program implementation-3 days -Ensure consistent and accurate information dissemination on various activities at the PPM to the participants.)
2.0. Registration
| · Develop social media connectivity with all registrants and other participants | Peace and Wezi
| · Establish media desk for inquiries | Ibrahim and Mahlet
2.1. Opening Ceremony
| · Register all media personnel | Ibrahim
| · Brand the stage with PACA materials | Liz, Ibrahim, Peace, Wezi and Winta
| · Establish media position/stand | Ibrahim
| · Distribute speeches to media after presentation /delivery | Ibrahim
| · Establish two spots (PACA/3rd PPM branded) for interviews | Ibrahim, Winta and Wezi
2.2. Post opening ceremony - HIGH LEVEL press conference
| · Identify and brand a hall/room for the press conference | Mahlet, Ibrahim and Winta
| · Identify moderator for the press conference | ?
| · Identify and prepare speakers at the press conference | ?
2.3. Plenary/Side event( during the 3 days)
| · Tweet developing activities during plenary and at the side meeting | Peace, Wezi and Ibrahim
| · Publish significant activities on PACA Facebook wall | Peace, Wezi and Ibrahim
| · Develop a professionally designed daily bulletin of an A4 size paper; | Ibrahim and ?
| · Send E-copies to participants through their registered social media accounts | Peace
| · Print outs bulletin for distribution during breakfast. | Mahlet and Ibrahim
2.4. Market Place
| · Photo gallery developed for publication in PACA News, website and other PACA web portals | Ibrahim
2.5. Gala Night (celebrated agents of change, award of $15,000 and Dinner)
| · Develop a program outline for the occasion and distribute to participants (Lunch time of the day). | ?
| · Set up a public address system/ musical instrument in the venue | Ibrahim, Mahlet and Wezi
| · Brand the venue | Ibrahim, Peace, Winta and Wezi
| · Develop and print AU awards certificates | ?
| · Identify master of ceremony to moderate the occasion | ?
| · Develop Photo Gallery | Ibrahim and Magatte
| · Do video recording (10 minutes) | Ibrahim and Magatte
2.6. Closing ceremony of 3rd PPM
| · Development of program outline for the closing ceremony | ?
| · Media coverage of the ceremony | Ibrahim
| · Development of communique, outlining major decisions and outcomes. Distributed to media | ? ? and Ibrahim
3.0. Objective 3. Post 3rd PPM - Increase public awareness and stakeholder about the 3rd PACA PPM including decisions and major outcomes
| · Develop Press Release for publication on the AU website and web linked to all PACA web portals | Ibrahim, Peace and ?
| · Identify all media publicity-online, and publish on the PACA web portals | Ibrahim and Peace
| · A special Edition of 3rd PPM PACA News Edition published | Ibrahim and ?