Report on

PACA Pilot Country Activities

Inception Workshop

Dar es Salaam, Tanzania

10-11 June 2014

June, 2014

# Contents

1.	Executive Summary	1

2.	Workshop Background	4

3.	Workshop Process	6

Opening Session	6

Day 1 – Session I- Technical Briefs	8

Day 1 - Session II: AfricaAIMS	11

Day 1- Sessions III to IV– Breakout Sessions	14

Country Group Members	14

Mechanisms for implementing the AfricaAIMS in Country	14

Lead Institutions Responsible for Data Collection	17

Institutions Responsible for Aflatoxin Data Analysis	20

Dara Submission in Country	22

Institution Responsible for DATA verification and submission onto AfricaAIMS	23

Main Agro-Ecologial Zones for Data Collection	23

Capacity Needs for Implementing AfricaAIMS in country	24

REC Group Session	28

Day 2 – Session I: Recap of Day One	31

Day 2 – Session I:  Plenary Report Back	32

Day 2- Session II: Launch of PACA Website:	32

Day 2 – Session III: Country Led Situational Analysis and Group Discussions	33

Day 2- Session IV NAFSIP Reviews and Group Discussions	34

Day 2- Session V Timelines for implementing activities	36

Day 2- Session VI Plenary Presentation of agreed timelines	38

Country Led Situation Analysis:	38

NAFSIP Reviews	42

Agreed Timelines	42

Day 2- Closing Session	44

4.	Workshop Participants	0

5.	Agenda	0

6.	Annexes	5

Annex 1: AfricaAIMS Parallel Breakout Session Template	5

Annex 2: Situational Analysis, NAFSIP Reviews and timelines -Parallel Breakout Session Template	7

Annex 3: Regional Economic Communities Breakout Session Template	9

Annex 4: PACA- pilot country laboratory capacity for aflatoxin testing and diagnosis	11

Annex 5: AfricaAIMS selection guideline for Country trainees	14

Annex 6: Africa Union Speech (Opening Session)	15

Annex 7: EAC Speech	22

OPENING REMARKS	22

Annex 8: The East African Community Regional Aflatoxin Project	28

# List of Tables

Table 1. Group Members	14

Table 2: Mechanisms for Implementing AfricaAims - Tanzania	15

Table 3: Mechanisms for Implementing AfricaAIMS - Uganda	16

Table 4: Lead Institutions Responsible for Data Collection in Country	17

Table 5: Institutions for Collecting and Submitting Data in Tanzania	21

Table 6: Laboratory Gap Capacity in Tanzania	26

Table 7: Trainees for AfricaAIMS- Uganda	27

Table 8: Proposed NAFSIP Review Methodology/Steps	35

Table 9: MAPAC Development Process in Relation to PACA Guidelines for Situation Analysis	39

Table 10: Senegal Steps and Timelines for Situation Analysis	40

Table 11: Tanzania Timelines for implementations of activities	42

Table 12: Next Steps	44

# List of Figures

Figure 1: Opening Session 	6

Figure 2: CAADP Implementation Progress	9

Figure 3: Aflatoxin Integrated Mitigation Options	10

Figure 4: Suggested Country Implementation Steps	11

Figure 5: AfricaAIMS Methodology	12

Figure 6: AU-IBAR ARIS II Products	13

Figure 7:Malawi Data Submission Process	22

Figure 8: Malawi Main Groundnut Producing Areas and Distribution of Aflatoxin Contamination	23

Figure 9: REC and AUC Group Session	28

Figure 10: PACA Website	32

Figure 11: Proposed Timeline for Country Activity Implementatio	37

Figure 12: Closing Session	45

# List of Abbreviations and Acronyms

| AfricaAIMS | Africa Aflatoxin Information Management System |
| --- | --- |
| AUC | African Union Commission |
| CAADP | Comprehensive Africa Agriculture Development Programme |
| COMESA | Common Market for Eastern and Southern Africa |
| DARS | Department of Agricultural Research Services |
| DPV | Directorate of Plant Protection (Senegal) |
| ECOWAS | Economic Community Of West African States |
| ELISA | Enzyme Linked Immuno Sorbent Assay |
| FAO | Food and Agriculture Organisation |
| FSQA | The Food Safety and Quality Authority (Gambia) |
| GBoS |  |
| GGC | Gambia Groundnut Cooperation |
| GRA |  |
| ICRISAT | The International Crops Research Institute for the Semi-Arid Tropics |
| IITA | The International Institute of Tropical Agriculture |
| KCH |  |
| KCMC |  |
| MAFC |  |
| MAFC-PHS |  |
| MAPAC | Malawi Program for Aflatoxin Control |
| MBS | Malawi Bureau of Standards |
| MDGs | Millennium Development Goals |
| MoA | Ministry of Agriculture (Gambia) |
| MoAFS | Ministry of Agriculture and Food Security (of Malawi) |
| MoH | Ministry of Health |
| MoHSW |  |
| MoTIE |  |
| MRA | Malawi Revenue Authority |
| MRC |  |
| MUHAS |  |
| NAFSIPs | National Agriculture and Food Security Investment Plans |
| NaNa | National Nutrition Agency (of Gambia) |
| NARI | National Agriculture Research Institute (of Gambia) |
| NEPAD | The New Partnership for Africa's Development |
| NFRA |  |
| NGO | Non-Governmental Organisation |
| NIMR |  |
| NMIST |  |
| NPCA | NEPAD Planning and Coordinating Agency |
| NPPO |  |
| NSO | National Statistics Office (of Malawi) |
| PACA | Partnership for Aflatoxin Control in Africa |
| PHS |  |
| Ppb | parts-per-billion |
| PRDCC |  |
| QECH |  |
| SPS | Sanitary and Phyto-sanitary |
| TANTRADE |  |
| TBS |  |
| TFDA | Tanzania Food and Drugs Authority |
| TFNC |  |
| TRA |  |
| UNBS |  |
| WFP | World Food Program (of the United Nations) |

# Executive Summary

At the 7th CAADP PP, African Leaders recognized the significant threats that Aflatoxins cause to trade, agriculture and the health of the populations, therefore, called for the establishment of an African-led Partnership for Aflatoxin Control. On 31 October 2012, Ministers of Agriculture and Ministers of Trade launched the Partnership for Aflatoxin Control in Africa.

PACA has since developed its 10 year Strategy in consultation with stakeholders across Africa. Through its 4 year Mid-Term Strategic Plan (2014-2017), PACA will, in 2014, initiate three major activities in five pilot countries (Gambia, Senegal, Malawi, Tanzania and Uganda), the activities are:

Activity 1: Establish Africa Aflatoxin Information Management System (AfricaAIMS);

Activity 2: Support country-led aflatoxin situation analysis and action plan;

Activity 3: Mainstream aflatoxin control through the PACA initiative in CAADP National Agriculture and Food Security Investment Plans (NAFSIPs).

On 10-11 June 2014, Africa Union convened Regional Economic Communities and PACA Pilot Countries to sensitize pilot countries on the activities planned for in 2014; to kick-start the implementation process; agree on the methodology for the implementation of AfricaAIMS; and agree on a timeline for the implementation of all three Pilot-Country activities.

Member States and RECs were presented with overviews of each activity and proposed methodology for implementation as discussed below:

Activity 1: Delegates acknowledged that one of the major challenges in mitigating aflatoxin in Africa is the lack of adequate information and harmonized data collection on the subject. Yet information is needed to inform policy and interventions; inform prioritization of resource allocation; and promote country capacity and awareness on the aflatoxin issue. Delegates therefore embraced the proposal of establishing an AfricaAIMS which will generate Africa owned data to inform policy and interventions; inform prioritization of resource allocation; promote country capacity and awareness on the aflatoxin issue. A methodology for implementing AfricaAIMS was presented and adopted by delegates with minor modifications.

Activity 2: In was noted that the Country-led situation analysis will assist Member States to generate empirical evidence on existing aflatoxin prevalence, legislation, policy and regulation, management practices and other existing control mechanisms that can effectively inform interventions.  Therefore the country-led analysis will catalyze strategic action in countries affected by aflatoxin by informing country leadership across stakeholder groups about necessary actions they can take; identify existing programs that can integrate aflatoxin control measures; and avoid duplication of effort. The Country-led situational analysis will also provide the necessary input to align aflatoxin control with broader food safety and SPS issues within countries. Possible methodologies and phases for implementing the Situational Analysis were presented and adopted at the workshop which includes:

Phase 1. Identify Key crops of concern

Phase 2. Determine the prevalence, distribution of aflatoxin

Phase 3. Characterize risks of aflatoxin contamination and exposure

Phase 4. Estimate economic impact due to aflatoxin contamination

Phase 5. Identify and prioritise opportunities for aflatoxin control

Phase 6. Conduct stakeholder workshop to communicate and validate findings and Identify priority action

Activity 3: The African Union Commission and RECs called upon its Member States to mainstream aflatoxins into the National Agriculture and Food Security Investment Plans (NAFSIPs) of CAADP and other relevant health and trade frameworks in order to address aflatoxins in a more sustainable and comprehensive fashion. It was noted that, by so doing, Member States will ease the process of identifying gaps for aflatoxin interventions in country policies; increase national investment in aflatoxin issues and attract other funds for country aflatoxin initiatives; facilitate the alignment of aflatoxin interventions and projects with country priorities through NAFSIPs and ensure that political leadership and ownership of aflatoxin issues at country level is established.

The PACA Secretariat proposed steps for implementing the NAFSIP reviews which were welcomed and adopted by the workshop delegates as detailed below:

Step 1: Roundtable Discussions will be conducted to inform and get endorsement from Country officials of the processes envisioned for implementing activities in Country as well as to agree on timelines, roles and responsibilities to be assumed by the Country’s Government Ministries, AUC, NEPAD and RECs in the implementation process.

Step 2: PACA will assist countries in contracting national consultants to facilitate the country process of NAFSIP reviews including engagement with stakeholder and CAADP Focal Point in finding gaps in the NAFSIP that need to be strengthened in terms of Food Safety and specifically aflatoxin mitigation

Step 3: PACA will assist Pilot Countries in organizing a NAFSIP Review Workshop which will enable the development of a comprehensive Food Safety and Aflatoxin Strategy and Investment Programme to support implementation of the country NAFSIPs through a consultative process

Step 4: Costing Exercise will enable countries to cost each intervention area as identified in the National Aflatoxin Strategy imbedded in the NAFSIP

Step 5: A Business Meeting will be convened with representatives from National Government, Development Partners, private sector and other relevant stakeholders to agree on priority areas and commit funding

Step 6: Implementation will be tracked through the CAADP Results Framework; through Country M&E Systems; and PACA M&E and AfricaAIMS

In conclusion, delegates at the workshop adopted all activities as suggested by PACA Secretariat including the timelines presented (with minor changes) which will ensure that all 5 PACA Pilot Countries implement the proposed three activities within 2014 commencing in June to November 2014.

# Workshop Background

Aflatoxins are naturally occurring fungal metabolites produced by strains of Aspergillus flavus and A. parasiticus, which are acutely and chronically toxic, immunosuppressive, mutagenic and carcinogenic compounds that affect diverse foods and feeds. Due to these health risks, aflatoxins have therefore proven to be a major barrier in linking African farmers to markets as they prevent commodities from meeting international, regional and local regulations and standards governing agricultural trade and food safety.

Cognizant of these problems, in March 2011 at the 7th Comprehensive Africa Agriculture Development Programme (CAADP) Partnership Platform, the African Union Commission was urged to oversee the establishment of a Continental SPS Working Group to mainstream sanitary/phytosanitary matters in the CAADP framework and establish an Africa-led Partnership for Aflatoxin Control. It was through this call that the Partnership for Aflatoxin Control in Africa (PACA) was established. PACA is therefore an innovative consortium aimed at coordinating and supporting aflatoxin mitigation and management across the health, agriculture and trade sectors in Africa. PACA’s overall aim is to support agricultural development, safeguard consumer health and facilitate trade by catalyzing, coordinating and increasing effective aflatoxin control along the agricultural value chains in Africa.

In line with its Mid-Term Strategic Plan (2014-2017), PACA will, in 2014, initiate the implementation of activities for aflatoxin mitigation in 5 pilot countries. Therefore, the PACA Secretariat in close consultation with COMESA, ECOWAS, EAC, SADC and with inputs from participants at the 10th CAADP PP underwent a process of selecting pilot countries. The following countries were selected to be part of PACA Pilot Countries: Gambia, Malawi, Senegal, Tanzania and Uganda. PACA will initiate the following activities in its pilot countries 2014:

- Undertake country-led aflatoxin situation analysis as part of understanding and strengthening the national food safety control systems.

- Mainstreaming aflatoxin issues in the CAADP framework through the review of National Agricultural and Food Security Investment Plans (NAFSIPs) and relevant health and nutrition frameworks

- Establishing Africa Aflatoxin Information Management System (AfricaAIMS) to enhance access to quality data, monitoring, evaluation and mutual accountability in the management of aflatoxins on the continent.

In addition, PACA will also assist Countries in a establish PACA country entities (working groups) through existing CAADP structures.

On 10-11 June 2014 in Dar Es Salaam Tanzania,Kunduchi Hotel,the AUC convened a PACA Country Activities inception workshop with PACA Pilot Countries and Regional Economic Communities. The objectives of the Country Activities Inception Workshop were to:

Objectives:

- Sensitize pilot countries on the activities planned for in 2014 and kick-start the implementation process;

- Agree on the methodology for the implementation of AfricaAIMS; and

- Agree on a timeline for the implementation of all three Pilot-Country activities

The PACA Country Activities Inception Workshop was attended by thirty nine (39) delegates, including:

- AUC: 6 delegates representing the Department of Rural Economy and Agriculture, Department of Trade and Industry, Department of Social Affairs and the Directorate of Programming, Budgeting Finance Administration. AUC was also represented by Technical Offices such as the Africa Union Inter-African Bureau of Animal Resource (AU-IBAR) and Inter - African Phytosanitary Council of African Union (AU-IAPSC).

- RECs: 3 Delegates representing the East African Community and the Common Market for Eastern and Southern Africa (COMESA).

- Member States: represented by:

  - Gambia – 4 delegates representing the Ministry of Agriculture, the Ministry of Health, the Ministry of Trade as well as one representative from the Food Safety Authority reporting to the Office of the President and Cabinet

  - Malawi- 5 delegates represented by the Ministries of Agriculture, Trade and Health

  - Senegal – 6 delegates represented by the Ministries of health, trade and agriculture as well as health practitioner

  - Tanzania – 5 delegates represented by the Ministries of Agriculture, Trade and Health

  - Uganda – 6 delegates represented by the Ministries of Agriculture, Trade and Health as well as PACA regional consultant on aflatoxin capacity and policy landscape in COMESA, ECOWAS, EAC and SADC

- Development Partners: 1 delegate from Meridian Institute

- AUC-PACA secretariat- 3 delegates from the PACA Secretariat based in AUC were present

# Workshop Process

The workshop was designed to be participatory and consultative in order to get perspectives from the health, trade and agriculture sectors, this is evident in the representation of participants. Each session of the workshop was divided into a scene setting section, a question and answer session and guided group discussions which were informed by templates that were provided before and during the workshop. Breakout sessions were typically clustered according to countries and AUC/REC groupings. All groups were encouraged to share their breakout session discussions in plenary in order to foster the spirit of sharing lessons among the different pilot countries. In addition, to increase the participation of delegates during the workshop, REC and country representatives were encouraged to chair various sessions.

Below is a summary of the workshop and outcomes from each session. Presentations made at the workshop can be accessed on http://www.aflatoxinpartnership.org

## Opening Session

The opening session was chaired by Mr. Raymond Wigenge, Director of Food Safety, Tanzania Food and Drugs Authority, Ministry of Health and Social Welfare, who invited the various speakers to give their remarks

Figure 1: Opening Session - From left to right: Mr. David Wafula, Mr. Raymond Wigenge, Dr. Janet Edeme, Ms. Martha Byanyima

Welcome Note: Dr.  Janet Edeme, Head of Division, Rural Economy and Agriculture, AUC

Dr. Edeme congratulated African leaders on showing their commitment to mitigating aflatoxin by availing technocrats within their various Ministries to attend the workshop. Dr. Edeme emphasized that one of the biggest challenges in mitigating aflatoxins is the the lack of adequate information and harmonized data collection on the subject. She therefore encrouraged Member States to embrace the creation of the AfricaAIMS which will generate Africa owned data to inform policy and interventions; inform prioritization of resource allocation; promote country capacity and awareness on the aflatoxin issue. Furthermore, Dr. Edeme highlighted the Year of Agriculture and Food Security whereby, in 2014, African Heads of States have chosen to reaffirme their commitment to increase agricultural production, productivity, food and nutrition security thereby combating hunger, malnutrition and poverty. It was stated that PACA, in partnership with its pilot countries, will contribute to the common objectives for the year of agriculture and food security through the review of National Agriculture and Food Security Investment Plans to identify opportunities where aflatoxin mitigation strategies can help achieve national goals related to agricultural productivity, trade, and public health.  In conclusions, Dr. Janet encouraged the pilot countries to avail their experiences in 2014 to other countries elsewhere in Africa in order to accelerate efforts to reduce aflatoxin contamination across the continent.

Opening Remarks: Ms. Martha Byanyima, SPS Expert - IPPSD COMESA Secretariat COMESA

Ms. Byanyima welcomed participants to the workshop. Ms. Byanyima explained how COMESA, being a trade organization views the importance of addressing aflatoxins in the broad context of food safety and putting into consideration Sanitary & Phyto-Sanitary (SPS) issues. It was highlighted that SPS issues pose Non-Tariff Barriers (NTB) to increase regional and international trade.  Furthermore, it was also emphasized that there is need to strike a balance between restrictions for trade policy versus protectionism because the two are not mutually exclusive but mutually supportive. In conclusion, Ms. Byanyima encouraged Member States to actively engage the private sector in the plight of mitigating aflatoxins on the continent.

Opening Remarks: Mr. David Wafula Agricultural Specialist, East African Community, EAC

Mr. Wafula welcomed the participants on behalf of Hon. Jesca Eriyo, the EAC Deputy Secretary General. Mr. Wafula congratulated the Republics of Gambia, Malawi, Senegal, Uganda and the United Republic of Tanzania for being selected as PACA Pilot countries.  He urged the selected countries to seize the opportunity presented by PACA and provide a model that can be replicated in other African countries. Furthermore, it was noted how critical the role of sharing information to inform evidence-based decision-making is, he therefore welcomed the establishment of the Africa Aflatoxin Information Management System (AfricaAIMS). Mr. Wafula also urged Member States to mainstream the Aflatoxin agenda in the national CAADP Compacts and Investment Plans to ensure that they receive the desired priority and attention.

Mr. Wafula informed the delegates that in cognizance of the magnitude and impacts of Aflatoxin, the EAC 27th Council of Ministers meeting held in 2013, directed the EAC Secretariat to design and implement a regional project aimed at preventing and controlling adverse impacts of Aflatoxin along the food and feed value chains.  With the support of USAID, Regional Office for East Africa, the Secretariat has moved with speed to prioritize and address the directive of the Council of Ministers.  It was therefore noted that The EAC Aflatoxin Project (see annex 8) is one of EAC’s flagship projects designed to address the multi-faceted impacts and effects of aflatoxin. Mr. Wafula informed the meeting that one of the key outputs of the project on Aflatoxin will be the development of the EAC Regional Policy on Aflatoxin abatement. It was mentioned that the focus of the EAC Aflatoxin project and the PACA thematic areas are complementary and mutually supportive.

In conclusion, Mr. Wafula re-affirmed EAC’s commitment to support, engage in and contribute towards implementation of interventions led by PACA.

Host Country Welcome Remarks: Mr. Raymond Wigenge, Director of Food Safety,Tanzania Food and Drugs Authority, Ministry of Health and Social Welfare

Mr. Wigenge reaffirmed the commitment of the Government of Tanzania in mitigating the aflatoxin problem. Mr. Wigenge welcomed all participants to the United Republic of Tanzania and wished all delegates successful deliberations in the duration of the workshop.

Meeting Objectives: Mrs. Wezi Chunga-Sambo-PACA Program Officer, AUC

Mrs. Chunga-Sambo welcomed all delegates and proceeded to offering the structure of the workshop. She gave an overview of the background documents, the agenda and templates that would guide some of the break-out session. She encouraged all delegates to interact freely and to actively contribute to the discussions. Mrs. Chunga-Sambo highlighted the objective as follows:

- Sensitize pilot countries on the activities planned for in 2014 and kick-start the implementation process;

- Agree on the methodology for the implementation of AfricaAIMS; and

- Agree on a timeline for the implementation of all three Pilot-Country activities

## Day 1 – Session I- Technical Briefs

Session one on day one helped to set the scene before proceeding into discussions. The following presentations were given and are summarized below

Session I Presentation 1. PACA- Flagship program of CAADP - Dr. Janet Edeme, Head of Division, Rural Economy and Agriculture, AUC

Figure 2: CAADP Implementation Progress

Dr. Edeme presented on the Comprehensive African Agriculture Development Program and specifically highlighted the progress of CAADP in the past decade (see figure 2), especially putting into context 2014 as the Year of Agriculture and Food Security which has coincided with the 10th year of implementing CAADP in Countries.

Slide 1

It was recognised that CAADP is an African owned and led strategic agenda which has proved to be a powerful tool of advocacy asserting the strategic importance of agricultural transformation in Africa. It was noteted that now thanks largely to the instrumentality of CAADP, it is fashionable to talk of agricultural development as a priority which was not the case before. The year of Agriculture and food security is an opportunity for all Africans to reflect on the past decade of experience with CAADP, highlight key lessons and acknowledge its value addition and its contributions thus far; taking stock of the current situation, opportunities and challenges. The common goal for the next decade in implementing the CAADP is “Towards setting 2025 Africa Accelerated Agricultural Growth and Transformation Goals (3AGTG)”. It was therefore noted that althought a lot has been done in the past decade, a lot still needs to be done in order to reach the 3AGTG by 2015. Some of the measures AUC has put in place to reach the 2025 vision, is through the establishment of flagship programs to assist countries in addressing key gaps in order to achieve the 2025 vision. One of the CAADP flagship programs established by AUC is the Partnership for Aflatoxin Control in Africa whichwill assist countries in addressing the following areas through the general food safety lense: increase production and productivity; increase value addition of produce along the agricultural value chain; increase trade; increase resilience and reduced vulnerability and; increase food security.

Session I Presnetation 2.Overview of PACA (PACA Strategy and Strategic Plan) – Dr. Amare Ayalew, Program Manager, PACA Secretariat, AUC

Dr. Ayalew gave an overview of the vexing problem of aflatoxin on Africa’s health, trade and agriculture, he further elaborated how aflatoxins affect food and nutrition security. He gave examples of the effects of aflatoxin on trade by stating that Africa loses US$450 million per year from lost export trade due to aflatoxins. In addition, he noted that aflatoxins also have a notorious impact on public health (fatal at high concentrations, can cause liver cancer and is linked to stunted growth and being underweight in children).

Figure 3: Aflatoxin Integrated Mitigation Options

Dr. Ayalew said that factors contributing to the aflatoxin challenge in Africa include conducive climatic conditions, traditional crop production practices, inadequate harvesting, drying and storage practices, dietary practices, policy and institutional capacity, and lack of awareness about aflatoxin.

Slide 2

Dr. Ayalew appreciated that the aflatoxin challenge is cross sectoral and complex therfore the mitigation of aflatoxins can also only be effective if a combination of interventions across the value chain are applied. He therefore recommended that the management of aflatoxin should be designed in such a way that it is comprehensive, integrated and coordinated. Furthermore, Dr. Amare highlighted the PACA Strategy (2013-2022) and the PACA Strategic Plan (2014-2017) which depicts PACA as an innovative consortium aiming at coordinating aflatoxin mitigation and management across health, agriculture and trade sectors in Africa. It was noted that PACA aims at adapting proven solutions, and identifying new ones, that will work for the African situation, and therefore attain PACA’s vision of “Africa free from the harmful effects of aflatoxins.”

Dr. Amare further enlightened the delegates of the three major activities that PACA will support its pilot countries in implementingin 2014. He informed the participants on the methodology that was used in seelcting pilot countries, which was inclusive, consutlative and transparent. In conclusion, Dr. Amare encouraged countries to embrace the implementtntation of the PACA activities.

Day 1: Session I Presentation 3.PACA Pilot Country Activities for 2014 – Mrs. Wezi Chunga-Sambo, Program Officer, PACA Secretariat, AUC

Mrs. Chunga-Sambo, gave an overview of the PACA activities to be implemented in country in 2014 which have been extrapolated from the PACA Strategy and PACA Strategic Plan and finally endorsed by the PACA Steering Committee.

Figure 4: Suggested Country Implementation Steps

It was highlighted that the activities should be taken as a package with one activity leading into the other. In this light, Mrs. Chunga-Sambo explained how the Situation Analysis results will inform the gap analysis in the NAFSIP review and the AfricaAIMS will build capacity to enable impact assessment of activities chosen by country in the NAFSIP for mitigating aflatoxins. Countries were encouraged to implement most of the outlined activities by October 2014 in order to report progress at the PACA Platform Meeting on 7-9 October, 2014.

## Day 1 - Session II: AfricaAIMS

One of the major challenges in mitigating aflatoxin in Africa is the lack of adequate information and harmonized data collection on the subject. Yet information is needed to inform policy and interventions; inform prioritization of resource allocation; promote country capacity and awareness on the aflatoxin issue. Through the PACA initiative, the African Union Commission will establish an Africa Aflatoxin Information Management System (AfricaAIMS) that will serve as a “one stop shop” information harbor for aflatoxin information in the health, trade and agriculture sectors. Data on the AfricaAIMS will be “home-grown” owned by AU Member States and respective Regional Economic Communities (RECs). The information on the AfricaAIMS will serve policy makers, regulatory bodies, potential investors, technical agencies (health, trade and agriculture), researchers, farmers, civil society organizations (CSOs), non-governmental organizations (NGOs), private sector partners along the value chain and other interested parties.

Session II Presentation 1: Importance of establishing an Africa owned information management system and Methodology/ Implementation Plan – Dr. Benoit Gnolonfin, Technical Officer, PACA Secretariat, AUC.

Figure 5: AfricaAIMS Methodology

Dr. Benoit gave an overview of the importance of establish an African Owned information Management System. Some of the benefits highlighted were: the AfricaAIMS will promote public awareness, advocacy and communication on aflatoxin prevalence and risk; provide evidence for the formulation of good legislation and policies and interventions; advocate for investment; promote regional and intra-regional trade; assist countries in meeting international obligation on food standards to enhance global trade; provide early warning systems for aflatoxin outbreaks; assist countries in monitoring and evaluating the impact of aflatoxin mitigation interventions in countries.

Dr. Gnolonfin went further to highlight the suggested methodology to be used in collecting, analysis and submitting data in country. The presentation detailed types of value chains that data will be collected from, it was deduced that data will be collected from the key value chain in the pilot countries such as peanuts, maize and rice. Furthermore, Dr. Gnolonfin highlighted the sampling protocol whereby, for example, maize and groundnut stored in bags: where there are less than 10 bags, incremental portions will be taken from each bag, and where the number of bags is >10, incremental portions will be taken from well distributed NN bags (where N = the number of bags). The sampling protocol also included guidance on sample collection methods for sampling sites, random sampling, record-keeping, storage of samples, labelling of and transportation of samples.  Dr. Benoit also proceeded to give an overview of the Aflatoxin analysis methods that exist and the recommended method based criteria of affordability, accuracy and expertise required for analysis. It was recommended that Vicam be used for analysis as it fit the criteria. Dr. Gnolonfin also gave various options for data analysis and data submission onto ARIS II.  It was recommended that SPSS for Window version 16.0 (SPSS, Chicago, IL) be used for statistical analyses. Analysis of variance (ANOVA) will be performed using Kruskal Wallis rank sum test. Mean total aflatoxin will be separated with Turkey’s honest significance difference (HSD) test (p=0.05). Nonparametric correlation test will be performed to evaluate interactions between total aflatoxin and altitude (AEZ) of sampling. Pearson correlation test will also be performed to determine relationship among the parameters. It was also recommended that Data submission to PACA through ARIS II should be made through country focal points who will submit data and other related information to PACA through AfricaAIMS. Data sets will be submitted from regional focal points (which can be organized according to agro-ecological zones) to an institution selected by country to verify the data and subsequently to the focal point. This will be similar for data collected in the health, trade and agriculture sector.

Products of ARIS II/ AfricaAIMS

A: Easy to Read Visual Charts

B: Risk Maps

C: Weekly Reports

D: Quarterly Digests and Year Book

Session II Presentation 2: AU-IBAR’s ARIS II and how it Works – Mr. Philippe Ouedraogo, Information Systems, AU-IBAR

Mr. Ouedraogo’s presentation gave an overview of the Animal Resource Information System (ARIS II) of AU-IBAR which has been identified by PACA as an ideal system to host the Africa Aflatoxin Data Management System (AfricaAIMS). It was noted that RIS II is a decentralized information management approach which enables AU Member States at a national and sub-national level, RECs and AUC to be self-sufficient in standardized and swift information flow. Based on the methodology endorsed by the PACA Country Activities Inception Workshop, PACA, in consultation with AU-IBAR will develop an aflatoxin module which will be initially hosted on version II of ARIS II at AU-IBAR.

Figure 6: AU-IBAR ARIS II Products

Mr. Ouedraogo highlighted that as with all information systems, the critical ingredient is data. The information that feeds ARIS II is drawn from structures that have been established at country and regional levels, and inclusive of international organizations.  Information is fed at each level (the farm level, district level, national, regional etc.) either electronically for online users or by hand for off-line users. For each level of the information collection system, there are access points and check points for information validation and clearance. It was noted that data is constantly being fed into the ARIS II system to produce up to date information. The ARIS II data collection system is currently in place in 24 countries (as of 2012).  From the information entered into ARIS II, AU-IBAR is able to generate several publications which allow for evidence based policy making. These include: Weekly disease Outbreak summaries, risk maps, quarterly digests and Pan-African Yearbooks on animal health (see slide 6).

## Day 1- Sessions III to IV– Breakout Sessions

Based on the presentation made in session II the RECs and the Countries engaged in a working session in breakout groups. The RECs with AUC congregated in one group and each of the countries congregated in separate groups, there were therefore 6 groups in total as follows:

- Group 1: REC and AUC Group

- Group 2: Gambia

- Group 3: Malawi

- Group 4: Senegal

- Group 5: Tanzania

- Group 6: Uganda

The PACA Secretariat provided templates to the 5 Pilot Countries before the workshop and during the workshop to help guide the discussions. Ms. Wezi Chunga-Sambo explained the templates to the countries and encouraged them to discuss within their group and answer all questions to be presented in plenary, see annex 1 and 2. Below is a summary of the discussions:

### Country Group Members

Table 1. Group Members

| Gambia -Grp 2 | Sana Jawara, Chief Public Health Officer, Ministry of Health and Social Welfare; Zainab Jallow, Ag. Director General, Food Safety and Quality Authority; Ndey Naffie Ceesay, Principal Economist, Ministry of Trade, Industry, Regional Integration & Employment Momodou L. Darboe, Principal Research Officer Ministry of Agriculture (NARI) |
| --- | --- |
| Malawi-GRP 3 | Misheck Soko – Agriculture, Research; Daisi Kachingwe – Agriculture, CAADP FP ; Flora Dimba – Health; Helen Mlotha – Trade; Isaac B. Gokah – Trade |
| Senegal-GRP 4 | Dr Amadou Lamine Senghor; PrAhmadou Dem; M. Abdoulaye Sy; Dr BabacarBeye; M MagatteNdoye; Dr Papa M. Diedhiou |
| Tanzania-GRP 5 | Lightness C. Muro- Ministry Of Agriculture F.C:Plant Health Services; Dr. Martin Kimanya – Nelson Mandela African Institution Of Science And Technology: Health&Agricuture; Immaculate J. Tarimo- Tanzania Food &Drug Authority- Health; Stella P. Lugongo – Ministry Of Industry And Trade; Dr. Omari Mponda – Naliendele Agricultural Research Institute- Division Of Research And Development, Ministry Of Agriculture F.C. |
| Uganda GRP 6 | Archileo Kaaya, Food Science; Tom Mugisha, Agriculture; Hakim Mufumbiro, Trade/Standards; Alex Bambona, Agriculture; Agaba Friday, Health; Maria Bisamaza, Academia Research |

### Mechanisms for implementing the AfricaAIMS in Country

- In your expert opinion, which of this data do you think can be collected in country and which ones cannot?

- Are there any data you think are important to be collected that have not been included in table 1? If so, list the data.

To these questions, most all the countries agreed to the data that was suggested for collection by the PACA Secretariat, below are further suggestions and remarks on the type of data to be collected in country (these are marked in red) below:

Gambia: All of the data suggested can be collected. It was noted that there is a National Cancer Registry in The Gambia for obtaining data on liver cancer incidences. Studies have also been done by the Medical Research Council using blood and urine samples to obtain biomarker information.

Malawi: Health: All data suggested by PACA can be collected except for liver cancer data which can only be collected to a limited extent due to capacity; Trade: All data suggested can be collected for formal trade, Agriculture: All data suggested can be collected.

Senegal: Trade: collect data on UEMOA, ECOWAS, “no border control for aflatoxin contamination” Agriculture: Aflatoxin control intervention (promotion of AflaSafe, use of oil filtration cartridge. Other data to be included that was not captured in the data suggested by the PACA Secretariat: Aflatoxin content in animal feed; Aflatoxin contamination in locally processed oil; Aflatoxin content of baby food

Table 2: Mechanisms for Implementing AfricaAims - Tanzania

| HEALTH | TRADE | AGRICULTURE |
| --- | --- | --- |
| Extent of consumption of aflatoxin prone food crops (maize, groundnuts) | Export rejections Internal food recalls or disposal/condemnation | Grain/kernel moisture content |
|  | Aflatoxin reduction interventions (GMP) at HACCP | Aflatoxin control interventions: GAP, New technologies |
| Risk minimizing intervention (HBV immunization, Nixtamalization |  |  |

Uganda:

Table 3: Mechanisms for Implementing AfricaAIMS - Uganda

| Health | Trade | Agriculture |
| --- | --- | --- |
| Liver cancer Yes, but need to put into consideration other related causes like alcohol, Hepatitis B, Birrhazia hence the need to also conduct the biomarker studies. For example, contaminated maize used to brew alcohol and yet the 2 cause cancer. | Aflatoxin standards in countries Standards are in place however, there is need for more national studies including risk analysis | Production levels Yes, |
| Aflatoxin levels in humans / bio-marker data (blood and/ urine) Yes. Ethical clearance is needed. There is the need to develop a protocol for collection and analysis for biomarkers | Volume of export and imports. Yes. | Aflatoxin contamination along the value chain (prevalence and levels) This should be for both crop and animals including feed |
| Extent of consumption of aflatoxin prone crops (maize, groundnut, etc.) Yes .Add other aflatoxin prone products like milk and eggs. | Export rejections Yes. However, this data may not easy to get due to inadequate documentation | Seed moisture content. Yes ut the word “seed” seems to be wrong. There is a national standard of 13.5% for grains except rice |
| Rate of childhood stunting (Diarrhea: presence of Cryptosporidium parvum, Giardia lamblia and EnteroaggregativeEscherichia coli); body weight, height. May not be used. The causal relationship will be difficult to justify. There are many causes of stunting and many are compounding factors including genetic factors. | Existence of free trade areas/ border control Yes. However the informal sectors are difficult to monitor | Drying, storage, processing and packaging, storage Yes, the infrastructure is mainly with Private sector and NGOs e.g. Milling Companies and WFP. |
| Others (HIV, HBV, Nodding Disease, Malaria, etc.) | Quantity of aflatoxin prone foods donated | Aflatoxin control interventions Yes. |
| Need for data on acute aflatoxicosis both in both humans and animals |  | Preharvest sensitization through GAP |
| Emphasis on Risk analysis | Emphasis on Risk analysis |  |

Based on the data you have identified as suitable for collection in your country, answer the following:

### Lead Institutions Responsible for Data Collection

Table 4: Lead Institutions Responsible for Data Collection in Country

|  | Health – who will collect the data and why | Trade - who will collect the data and why | Agriculture - who will collect the data and why |
| --- | --- | --- | --- |
| Country Responses | Liver cancer | Aflatoxin standards in countries | Production levels |
| Gambia | MoHSW (Dept of Planning & Information) | Gambia Standards Bureau | MoA – Dept. of Agriculture |
| Malawi | QECH (Have cancer unit) | MBS (Standard setting body) | MoAFS (responsible Institution) |
| Senegal | Faculty of Medicine (Department of Cancerology) Reason : have already done similar work on smaller sample | IITA (standards) (Asepex) and PRDCC Other issues |  |
| Tanzania | National Hospitals- MUHAS Regional – KCMC, Bugando District – health extension officers | TFDA, TBS |  |
| Uganda | •There is an existing Codex Focal Point and Secretariat (Uganda National Bureau of Standards (UNBS) •The PACA Focal person will be Prof. Kaaya, to coordinate collection of data and will be reporting to UNBS •A multisectoral taskforce comprising of health, agriculture and trade. •Each of these sectors will have one focal person who will be responsible for linking up the activities and also identifying participating institutions |  |  |
| Country Responses | Aflatoxin levels in humans / bio-marker data (blood and/ urine) | Volume of export and imports | Aflatoxin contamination along the value chain (prevalence and levels) |
| Gambia | MoHSW& MRC | MoTIE (Trade Information System), GBoS | MoA, MoTIE, GGC, FSQA |
| Malawi | KCH & QECH (Main Central Hospitals. KCH already collaborating with ICRISAT on a similar study) | MRA & NSO (Main source of export and import data) | MOAFS –DARS & MBS (responsible institutions (regulations) |
| Senegal | Faculty of Medicine (Department of Cancerology) Reason : have already done similar work on smaller sample | IITA (standards) (Asepex) and PRDCC Other issues | IITA Aflatoxin content along the value chain |
| Tanzania | Health Research Institutes NIMR, NMIST, MUHAS | TRA, TANTRADE, MAFC,PHS |  |
| Uganda | •There is an existing Codex Focal Point and Secretariat (Uganda National Bureau of Standards (UNBS) •The PACA Focal person will be Prof. Kaaya, to coordinate collection of data and will be reporting to UNBS •A multisectoral taskforce comprising of health, agriculture and trade. •Each of these sectors will have one focal person who will be responsible for linking up the activities and also identifying participating institutions |  |  |
| Country Responses | Extent of consumption of aflatoxin prone crops (maize, groundnut, etc.) | Export rejections | Seed moisture content |
| Gambia | GBoS | MoTIE& FSQA (Rapid Alert System) | NARI |
| Malawi | MoH, MoAFS, NSO (Collects basic data on the subject) | MoIT, NPPO & MBS (responsible notification institutions) | MoAFS – DARS & NFRA (responsible institution with capacity) |
| Senegal | Faculty of Medicine (Department of Cancerology) Reason : have already done similar work on smaller sample | IITA (standards) (Asepex) and PRDCC Other issues | Ancar (Extension agency): Grain Moisture, storage, packaging, etc. |
| Tanzania | (maize, groundnuts):TFNC | Internal food recalls or disposal/condemnation: TBS, TFDA |  |
| Uganda | •There is an existing Codex Focal Point and Secretariat (Uganda National Bureau of Standards (UNBS) •The PACA Focal person will be Prof. Kaaya, to coordinate collection of data and will be reporting to UNBS •A multisectoral taskforce comprising of health, agriculture and trade. •Each of these sectors will have one focal person who will be responsible for linking up the activities and also identifying participating institutions |  |  |
| Country Responses | Rate of childhood stunting (Diarrhea: presence of Cryptosporidium parvum, Giardia lamblia and EnteroaggregativeEscherichia coli); body weight, height. | Existence of free trade areas/ border control | Drying, storage, processing and packaging, storage |
| Gambia | MoHSW&NaNA | MoTIE& GRA (TBT Committee) | MoA, Farmer Field Schools &MoTIE |
| Malawi | MoH&Dept of Nutrition & HIV/AIDS (Oversight institutions on nutrition) | MoIT (responsible Institution) | Private Sector (NASFAM, FUM, Others as relevant) - Directly involved in these processes |
| Senegal | Faculty of Medicine (Department of Cancerology) Reason : have already done similar work on smaller sample | IITA (standards) (Asepex) and PRDCC Other issues | DPV Aflatoxin control intervention IITA filtration cartridge |
| Tanzania | TFNC, MUHAS, KCMC,Bugando, District and regional Hospitals | TBS,TFDA, MAFC-PHS |  |
| Uganda | •There is an existing Codex Focal Point and Secretariat (Uganda National Bureau of Standards (UNBS) •The PACA Focal person will be Prof. Kaaya, to coordinate collection of data and will be reporting to UNBS •A multisectoral taskforce comprising of health, agriculture and trade. •Each of these sectors will have one focal person who will be responsible for linking up the activities and also identifying participating institutions |  |  |
| Country Responses | Others (HIV, HBV, Nodding Disease, etc.) | Other | Aflatoxin control interventions |
| Gambia |  |  |  |
| Malawi | MoH (Responsible Ministry) |  | MAPAC (Coordinating programme) |
| Senegal | Faculty of Medicine (Department of Cancerology) Reason : have already done similar work on smaller sample |  | DPV Aflatoxin control intervention ITA filtration cartridge |
| Tanzania | MUHAS, Bugando, KCMC |  |  |
| Uganda | •There is an existing Codex Focal Point and Secretariat (Uganda National Bureau of Standards (UNBS) •The PACA Focal person will be Prof. Kaaya, to coordinate collection of data and will be reporting to UNBS •A multisectoral taskforce comprising of health, agriculture and trade. •Each of these sectors will have one focal person who will be responsible for linking up the activities and also identifying participating institutions |  |  |

### Institutions Responsible for Aflatoxin Data Analysis

Gambia: NARI, already established as an aflatoxin testing facility and the Gambia Groundnut Cooperation (GGC) quality control lab

Malawi: DARS and MBS

Senegal: IITA will analyze aflatoxin in locally processed oil, animal feed and baby food; In blood: Faculty of medicine (a person to be trained) Aflatoxin in peanut and peanut based commodities DPV, ITA, University

Tanzania:

Table 5: Institutions for Collecting and Submitting Data in Tanzania

| WHO? | WHY? |
| --- | --- |
| Tanzania Food and Drug Agency TFDA | Capacity, location, competency-Mandate |
| Government Chemical Laboratory | Capacity, location, competency Mandate |
| Nelson Mandela NMIST | Capacity, location, competency (North) |
| Tanzania Bureau of Standards TBS | Capacity, Location, competency Mandate |
| MAFC-DRD- ARI Naliendele | Capacity, location, competency (South)-National research mandate in groundnuts |

Uganda: Makerere University, Central Public Health Laboratory, Government Analytical laboratory, UNBS

### Dara Submission in Country

Countries were asked to clearly map out the data submission process and identify which institution or organization in country would be responsible for data submission in the three sectors (health, trade, agriculture) and to identify a central focal point for submission of data into AfricaAIMS.

Gambia: Agriculture (NARI, DoA), Health (DPI), Trade (Directorate of Trade, Gambia Standards Bureau), NaNA submit to FSQA (focal point) to submit to AfricaAIMS

Malawi:

Figure 7:Malawi Data Submission Process

Senegal: Institutions responsible for data submission: Health: Dr Dem to suggest somebody; Trade : Magatte Ndoye (Ministry of Commerce); Agriculture : Babacar Beye (IITA); Central focal point : Diedhiou (University); AfricaAIMS focal point : DPV (Lamine Senghor)

Data submission process: 1 : Data collector; 2 : focal point with copy to the group; 3 : central focal point; 4 : AfricaAims focal point

Tanzania: TFDA –Secretariat for National Mycotoxin Steering Committee; each centre to have aflatoxin coordinator who will organize sampling and delivery of data to TDFA

Uganda: UNBS will be the secretariat with the following ToR

- Functional link to PACA

- Coordination of the functions of  the focal person and task force

- Ensure timely Collection and submission of data

- Ensure quality assurance and due diligent of data

- Resource mobilization and support to the taskforce

Coordination of the functions of and taskforce

### Institution Responsible for DATA verification and submission onto AfricaAIMS

Countries were asked to discuss who they think will be the appropriate body/institution to be re responsible for data verification and submission at country level as an AfricaAIMS focal point

Gambia: FSQA

Malawi: MAPAC/PACA Country ATWG

Tanzania: Nelson Mandela Africa Institute of Science and technology NMIST

Senegal: DPV

Uganda: UNBS

### Main Agro-Ecologial Zones for Data Collection

Countries were asked to identify the main agro-ecological zones producing of main value chains (maize, groundnut) including animal feed value chains for poultry and fish

Gambia: Maize, rice and groundnuts grown in the rural areas (From North Bank East to Upper River Region)

Malawi: Maize: Country-wide ; Groundnuts: Main Groundnut producing areas and distribution of aflatoxin    contamination (see map below)

Figure 8: Malawi Main Groundnut Producing Areas and Distribution of Aflatoxin Contamination

Senegal:

1 - Irrigated agrosystems (river valley and Niayes zone)

2 – soudano-sahelian zone

3 – soudano-guinean zone

Tanzania:

Lake Zone – Shinyanga (Kahama, Bukombe),

Central Zone – Dodoma (Kongwa,Chamwino, Bahi,) Singida

Southern Zone – Mtwara( Masasi, Nanyumbu)

Western Zone – Kigoma, Tabora

Uganda:

- NorthEeasternDrylands (Maize/Gnuts)

- North Eastern savannah Grassland (maize)

3.	North Western Savannah Grassland Groundnuts & some maize)

4.	Parasavannahs (Maize and groundnuts)

5.	Kyoga Plains (Home of maize and groundnuts)

6.	Lake Victoria Crescent (Maize and Grounduts)

7.	Western savannak Grasslands (Maize and groundnuts)

8.	Pastoral Rangelands (Scanty maize and groundnuts)

9.	South Western Farmlands (Some maize and some groundnuts)

10.	Highland Ranges (Maize)

### Capacity Needs for Implementing AfricaAIMS in country

- Countries were asked to gauge country capacity gaps for implementing AfricaAIMS using the country lab capacity form (see annex 4). The following questions guided discussions in the groups and the responses in each Country Group is summarised below

Q1a) Equipment necessary for collecting and analysing data a identified in section 1a

Q1b) Human capacity needs for analysing data, collecting and or entering data for AfricaAIMS

Q2) Propose candidates to be trained in AfricaAIMS data submission in country

Gambia: Q1a: All (NARI not accredited, Thin Liquid Chromatography (TLC) method being used and High Performance Liquid Chromatography (HPLC) method not fully established)

- vicam / GPS / Probes / moisture meter / reagents and consumables / elisa system (Senegal intervention)

Q1b:Training at all levels (Inspectors, lab personnel and data entry)

Q2: Food Safety and Quality Authority, Ministry of Health, Ministry of Agriculture, Ministry of Trade, Gambia Bureau of Statistics, National Nutrition Agency

Malawi: Q1a) Vicam, Computers and associated Accessories plus Internet Routers (MAPAC AfricaAIMS focal point and other 2 sectors), Moisture metres, Sampling Spears, Health Sector equipment to be provided later

Q1b) Long term training of technicians and professionals

Q2)

- 2 delegates from trade (at least 1 delegate should be selected who has access to data on export/import rejection due to aflatoxin levels) (Bridget and 1 NSO statistics officer based in MoIT)

- 2 delegates from health (preferably medical doctors in central government) – to be provided later

- 3 delegates from agriculture (at sub-regional, regional and national level) – Misheck, Haraman, and Daisi)

- 1 delegate from bureau of standards/ food safety authority/ food and drug administration/ competent authority (To write to MBS)

- 3 delegates from reference labs (1 Bunda College – Agnes Mwangwela, 1CARS, 1BARS)

Senegal: (Q1a,b and Q2)Equipment Vicam to be purchased and existing equipment to be upgraded, GPS, Moisture meter, Probes, Lab supplies, reagents and consumables, Elisa-system (blood, urine), Compound Microscope and supplies (parasites),

Tanzania: :(Q1a, b and Q2)

Table 6: Laboratory Gap Capacity in Tanzania

| Location | Equipment | Maintenance | Access to reaents | Supplier | Method/SOP | Type of food | Range of afla ppb | No. of techn | Capability to support |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TFDA | HPLC |  | - | Known | HPLC, Yes | Maize/cereals, >1000 | 0.5-300 | none | Good |
| ARI Naliendele | Outsourced ELISA | - | Not | No | - | Gnuts,400 | ? | none | Good |
| NMIST | VICAM | OK | UNRELIABLE | KNOWN | Vicam, Yes | Maize | - | 0 | Good |
| Government C.L | HPLC | - | - | - | - | - | - | - |  |
| TBS | HPLC, LCMS | - |  |  |  |  |  |  |  |
| TFNC | HPLC |  |  |  |  |  |  |  |  |
| NMIST | HPLC, PCR |  |  |  |  |  |  |  |  |
| MUHAS | ELISA |  |  |  |  |  |  |  |  |

Uganda:

Table 7: Trainees for AfricaAIMS- Uganda

| # | Name | Title | Contact phone no |
| --- | --- | --- | --- |
| 1 | Jolly Hoona | Principal Veterinary Officer (Public Health) MAAIF | 0752 829034 |
| 2 | Alex Bambona | Head, Food & Nutrition, MAAIF | 0772 494725 |
| 3 | Fred Muzira | Agricultural Inspector, MAAIF | 0718 124618 |
| 4 | Tom Mugisa | CAADP Focal Person, OPM | 0772436683 |
| 5. | ArchileoKaaya | Professor, Makerere University | 0772440046 |
| 6 | Abel Atukwase | Senior Lecturer, Makerere University | 0774468261 |
| 7 | Agaba Friday | Food safety Coordinator, NDA/MoH | 0772691236 |
| 8 | Hakim Mufumbiro | Head Food and Agriculture Standards Division, UNBS | 0772513680 |
| 9 | Joseph Iberet | Analyst, UNBS | 0701066148 |
| 10 | Maria Bisamaza | Makerere University | 0774536950 |

Countries were asked to use the selection guideline for AfricaAIMS trainees (see annex 4) and to provide names of trainees to the PACA Secretariat by 20 June 2014.

### REC Group Session

#### Team Members

1. Frank Mugyenyi (chair) AUC

2. Martha Byanyima COMESA

3. Mabvuto Kango AUC

4. Janet Edeme AUC

5. Philip Ouedraogo-IBAR

6. David Wafula-EAC

7. Louis Murango-EAC

Figure 9: REC and AUC Group Session

The PACA Secretariat provided templates to the REC grouping before the workshop and during the workshop to help guide the discussions. Ms. Wezi Chunga-Sambo explained the templates to the REC group and encouraged the delegates to discuss and answer all questions to be presented in plenary, see annex 3. Below is a summary of the discussions:

The following questions were asked:

1. Regional Aflatoxin/Food Safety Action Plans: Share the status of aflatoxin action planning in your region, what has or is working well, what could be improved, and any suggestions you have for other regions based on your experience.

2. Identification of REC-PACA Joint Activities: From your respective focus areas and work plans at REC level and having looked at the PACA 2014/15 work plan and strategy, please suggest areas of mutual interest and collaboration for 2014/2015. Any suggestions for the out years (2016-17)?

3. Policy and Regulatory Landscape: Review and discuss the approach to and findings from the policy and regulatory scoping study recently conducted in the COMESA region.  PACA is interested in expanding this study to ECOWAS, SADC and EAC Member States.  Discuss how this can best be accomplished (i.e. can the RECs provide names and contact information for food safety focal points or SPS authorities in countries?).

4. Financing of Aflatoxin Situation Analysis and Action Plans: a)Review and discuss STDF Project Planning Grant and Project Grant opportunities, as well as other funding sources for aflatoxin situation and food control system analysis and action planning.

b) How can you support one or more of the 2015 pilot countries in your region to apply for a PPG to conduct a country-led aflatoxin situation analysis (due 18 July)?

c) What lead role can your REC be playing in an application for a regional project which makes the link between the country-level work and the regional aflatoxin action plans? Or propose how country / regional level plans could be linked to, and mainstreamed into, broader trade capacity building programmes (Aid for Trade, EIF, etc.)?

The following discussions ensued in the group

The EAST AFRICAN COMMUNITY (EAC)

The EAC has a flagship project in which they are developing a regional policy on aflatoxin. The objectives of the EAC Regional Project on Aflatoxin are:  their initiatives include:

- Development of EAC Regional Policy on Prevention and Control of Aflatoxins

- Establish the foundation for a Regional Bio-control Program in the EAC

- Build Capacity of the region on Aflatoxins Control and Prevention in the Region

- Build Capacity of the region on Aflatoxins Control and Prevention in the Region

  - Develop a regional policy;

  - Establish biocontrol mechanisms;

  - Undertake capacity building on prevention and control;

  - Scale up communication to create awareness.

EAC is collaborating with the International Institute of Tropical Agriculture (IITA) to ensure development of an evidence-based policy, standard and to ensure development of an evidence-based policy, technical papers and policy briefs are being developed in the areas of standards for food and feed, impacts on human and animal health, biocontrol and post-harvest handling, alternative uses and disposal systems, economic impact on trade, a communication strategy and Vaccinations/Immunization, Adoption of Hepatitis A&B Vaccination

EAC has constituted the Regional Experts Working Group on Aflatoxins (REWGA) which is mandated to provide technical and advisory guidance to EAC Sectoral Council on Agriculture and Food Security and key stakeholders in the region on prevention and control of aflatoxin in the EAC region. REWGA will work at a regional level to provide leadership for coordinating and monitoring strategic interventions on aflatoxin control. The composition of REWGA is multisectoral comprising of state and non-state actors in the areas of Public Health, Environment, the Food, Crops and Animal value chains, farmers, private sector, CSOs and international organisations, etc.

EAC is in the process of working with WHO to introduce vaccination for hepatitis A & B into member state national vaccination/immunization programs and plans. EAC are in the process of strengthening human resources by engaging a microbiologist and a logistician to provide the required technical support, , TORS have already been agreed and experts identified. Partners involved are IITAAT and WHO.

As part of the process, there are is a validation workshops with experts from Partner member states scheduled from or 16th-30th June to review technical papers on:

- Impacts of Aflatoxin on animal health

- Impacts of Aflatoxin on human health

- Aflatoxin and 1000 days

- Standards for food and feed

The EAC Regional Post-Harvest Handling and Storage Measures for Aflatoxin Abatement has been developed by experts drawn from EAC Partner States.  The main objectives of EAC draft regional post-harvest handling and storage measures for aflatoxin abatement are to;

- Support Partner States implement integrated systems of post-harvest handling, storage and processing methods to minimize aflatoxin contamination; and

- Improve knowledge of local scientists, farmers, storage operators,   processors, distributors and consumers about aflatoxin prevention and control measures.

The scope of the document encompasses post-harvest handling and storage measures for aflatoxin abatement in cereals, root crops, tree and oil crops and beverages. The document also contains guidelines for disposal of agricultural products that are highly contaminated with aflatoxin.

One of their strengths is the complementarity realized through partnerships, focused, communications component of the project and the participatory and inclusive EAC policy making process operating a very focused communication strategy alongside their programmes.

THE COMMON MARKET FOR EASTERN AND SOUTHERN AFRICA (COMESA)

The COMESA has:

- A unit for SPS

- Has SPS committee that assists ministers to determine priorities;

- COMESA also does surveillance and testing and has initiatives to improve the regulatory environment for bio pesticides.

Their work also includes:

- strengthening surveillance systems;

- improving sampling & analytical capabilities i.e. improving methodology

- providing technical support to Member States to close gaps in standards

  - In Rwanda recently convened SPS authorities who mainstreamed action plans into CAADP

  - they generate evidence , through economic analysis of SPS that can be used to make projections and make comparative analysis among the various available options

Challenges include coordination of country initiatives and handling pilots . Harmonizing policies is also a challenge as countries can commit but still implement in a varied married. As an incentive to encourage compliance, COMESA has moved towards development oriented approaches.

COMESA also compiles and shares best practices in cost reduction that can help Governments reduce operational costs. COMESA works closely with the private sector, a practice that ensures sustainability.

Priorities are determined by the challenges existing at the time examples include previous challenges with plant pests such as the fruit fly and problems with staples such as peanuts in Zambia and Malawi with aflatoxin that affected exports.

COMESA Noted that Public Private Partnerships (PPPs) is their best practice especially in horticulture

THE INTER - AFRICAN PHYTOSANITARY COUNCIL OF AFRICAN UNION (AU-IAPSC)

Like most intergovernmental organisations, IAPSC has the power to convene and they use this to promote the fight against aflatoxin. It is a policy of their director that every meeting should begin with some remarks on aflatoxin.

IAPSC is implementing a project that includes management of aflatoxin in the post-harvest period to address capacity building on the continent;

## Day 2 – Session I: Recap of Day One

Mr. Daisi Kachingwe, the Malawi CAADP Focal Point in the Ministry of Agriculture and Food Security gave an overview of the previous day’s discussions by summarizing the speeches and PowerPoint Presentations that were rendered on the first day of the Country Activities Inception workshop. Mr. Kachingwe captured the first day’s discussion in a colorful presentation demonstrated through pictures.

## Day 2 – Session I:  Plenary Report Back

This session was chaired by Mr. David Wafula who invited countries to present their previous day’s discussions (summarized above) in plenary. The Senegal Representative chaired the REC session by inviting Dr. Mabvuto Kango to present on behalf of the RECs and AUC.

Day 2- Session II: Launch of PACA Website:www.aflatoxinpartnership.org

Figure 10: PACA Website

Dr. Amare Ayalew addressed the audience by stating how Tanzania has become a symbol of PACA’s great achievements; this was in reference to the three great milestones that PACA has achieved in Dar es Salaam Tanzania which include the PACA Strategy Stakeholder Development Workshop, April 2013; The PACA Country Activities Inception Workshop and indeed the PACA Website launch on 11 June 2014. Dr. Ayalew informed the delegates that the PACA Secretariat is in the process of transitioning into the AUC, as such, the website that was ably hosted by Meridian Institute would now be managed by AUC.  Dr. Ayalew highlighted how the PACA Strategy (2013-2022) has identified the PACA Website to be a key tool to achieve effective communication. Therefore, the PACA Website will  include regular news stories about PACA’s plans, progress and achievements; a blog by the PACA Manager which highlights key issues and links these to the broader landscape in which PACA operates; and a regularly updated calendar of events which flags forthcoming events and archives past ones, amongst other content. It was also noted that in future, the website will host the AfricaAIMS which will further fulfil the purpose of the website which is to act as an:

- Information sharing tool

- One stop shop

- Information portal

- Flexible platform

Dr. Ayalew took the delegates through a virtual tour of the PACA website which has been designed on a v2.0 system. The website is therefore built on a flexible, open source platform (Drupal) to accommodate a growing web-based information portal; resources pages are designed to become a portal for information about PACA and aflatoxin control across Africa; the website has an interactive map of aflatoxin control activities in Africa; it enables stakeholders to easily access information about aflatoxin news and PACA activities; it is AUC-Based therefore, the AUC-PACA Secretariat has full control over content and can update on an ongoing basis.

In conclusion, Dr. Amare thanked the team at the PACA Secretariat that was behind the design of the website and who worked tirelessly to ensure the timely manner in which the website has been launched; this includes Ms. Winta Sintayehu, Mr. Rex Raimond and Ms. Robyn Paulekas.

## Day 2 – Session III: Country Led Situational Analysis and Group Discussions

For countries that have not yet conducted situational analyses, PACA will support its  pilot countries in conducting country-led food safety system and aflatoxin situation analysis and action planning by assisting countries to create empirical evidence on existing aflatoxin prevalence, legislation, policy and regulation, management practices and other existing control mechanisms that can effectively inform interventions.  PACA will work with national consultants and Aflatoxin Technical Working Groups to conduct the analyses in alignment with the guidance of the political and technical leadership of the country.

The country-led analysis will: catalyze strategic action in countries affected by aflatoxin by informing country leadership across stakeholder groups about necessary actions they can take; identify existing programs that can integrate aflatoxin control measures; and avoid duplication of efforts. The Situation Analysis will also provide the necessary input to align aflatoxin control with broader food safety and SPS issues within countries.

Presentation 1:Country-led situational analysis: Sharing lessons with past methodologies used for country analysis --- (PPT) Dr. Martin Kimanya, Ag. Dean School of Computational and Communication Science and Engineering (COCSE)

In 2011-2012, the PACA Secretariat through Meridian Institute commissioned an aflatoxin situation analyses for Tanzania and Nigeria. Dr. Kimanya was part of the team that undertook the situation analysis in Tanzania, therfore to foster the spirit of sharing lessions, Dr. Kimanya was encouraged by the PACA Secretariat to share lessions to the delegates at the Country Activities Inception Workshop. Dr. Kimanya took the delegates through the appproach that was taken in conducting the analysis iin 2012 in Tanzania which included:

- Review of documents

- Conduct high level meetings with stakeholders

- Interview key informants (farmers, traders, wholesalers, manufacturers)

- Generate prevalence data to determine regions of high contamination

- Stakeholders feedback (workshop)

Dr. Kimanya informed delegates that the outcomes of the Tanzania Situation Analysis helped in the formulation of the Tanzania National aflatoxin Strategy. Dr. Kimanya went further to eleaborate some of the challenges that were encountered in the collection and analysis of the data. In conclusion, Dr. Kimanya encouraged the country representatives to access the Tanzania and Nigeria situation analyses (which were also circulated at the workshop) on the PACA Website: http://www.aflatoxinpartnership.org/?q=node/168 and http://www.aflatoxinpartnership.org/?q=node/166

Presnetation 2:Proposed methodologies and steps for Situation Analysis– Dr. Benoit Gnolonfin, Technical Officer, PACA Secretariat, AUC

Dr. Gnolonfin outlined a proposed methodology for the country –led situational analyses by highlighting the major steps and phases to be taken in the analysis in order to ensure that a standardized and harmonised method is used across the 5 pilot countries, below are the suggested phases as presented by Dr. Gnolonfin

Phase 1. Identify Key crops of concern

Phase 2. Determine the prevalence, distribution of aflatoxin

Phase 3. Characterize risks of aflatoxin contamination and exposure

Phase 4. Estimate economic impact due to aflatoxin contamination

Phase 5. Identify and prioritise opportunities for aflatoxin control

Phase 6. Conduct stakeholder workshop to communicate and validate findings and Identify priority action

## Day 2- Session IV NAFSIP Reviews and Group Discussions

The aflatoxin challenge can be addressed effectively and in a more sustainable and comprehensive fashion if it is mainstreamed in existing frameworks and structures, such as CAADP National Agriculture and Food Security Investment Plans (NAFSIPs). Other frameworks that can be used for mainstreaming aflatoxin issues include, inter alia, the African Health Strategy, Scaling Up Nutrition (SUN), national food safety laws and regulations, and local agricultural extension and community health programs. In 2014, PACA will support its pilot countries’ efforts to mainstream aflatoxins and other food safety challenges into their CAADP NAFSIPs and relevant health and nutrition frameworks. By so doing, countries will:

- Ease the process of identifying gaps for aflatoxin interventions in country policies;

- Increase national investment in aflatoxin issues and attract other funds for country aflatoxin initiatives;

- Facilitate the alignment of aflatoxin interventions and projects with country priorities through NAFSIPs;

- Ensure that political leadership and ownership of aflatoxin issues at country level is established.

Presentation 1:Proposed methodology/steps for NAFSIP reviews (PPT) – Mrs. Wezi Chunga- Sambo, Program Officer, PACA Secretariat, AUC

Mrs. Wezi Chunga-Sambo gave an overview of the proposed NAFSIP review steps as highlighted below:

Table 8: Proposed NAFSIP Review Methodology/Steps

| Step | Objective/ Description |
| --- | --- |
| Roundtable Discussions | - Inform and get endorsement from Country officials of the processes envisioned for implementing activities in Country - Agree on roles and responsibilities to be assumed by the Country’s Government Ministries, AUC, NEPAD and RECs in the implementation process. - Agree on timelines, goals and targets for implementation - Plan and agree on stakeholder engagement during the implementation of activities especially in the validation of the situation analysis as well as the NAFSIP review process. |
| Hire Consultants | - To facilitate the country process of NAFSIP Reviews - Engage all necessary stakeholder with the direct leadership of the CAADP Focal Point - Propose gaps in the NAFSIP that need to be strengthened in terms of Food Safety and specifically aflatoxin mitigation |
| NAFSIP Review | To develop a comprehensive Food Safety and Aflatoxin Strategy and Investment Programme to support implementation of the country NAFSIPs |
| Costing Exercise | Through support of relevant partners such as FAO and COMESA (economic analysis tool or the FAO Investment Centre) countries will cost each intervention area prioritized through the NAFSIP reviews in order to identify budget gaps for the implementation of the Aflatoxin strategy embeded in the NAFSIP |
| Business Meeting | Convene Government, Development Partners, private sector and other relevant stakeholder to agree on priority areas and commit funding |
| Implementation | M&E to be tracked through the CAADP Results Framework; through Country M&E Systems; and PACA M&E and AfricaAIMS |

## Day 2- Session V Timelines for implementing activities

Presentation 1:Presentation on Proposed timeline for agreed country activities - Mrs. Wezi Chunga-Sambo, Program Officer, PACA Secretariat, AUC

Mrs Wezi Chunga-Sambo gave an overview of the timelines proposed for implementing the various activities that were agreed upon during the workshop. She encouraged Member States to view the implementation of the activities as a step by step process with one activity feeding into the other. She also noted that the timeline has been designed to enable the PACA Secretariat, AUC, RECs and NEPAD to service and engage the various schedules meetings/egagements which will be running back to back from one country to the other. In this light therefore, countries were asked to revise the timeline to fit into their national plan (see figure 11)

Figure 11: Proposed Timeline for Country Activity Implementation

## Day 2- Session VI Plenary Presentation of agreed timelines

Based on the country led situatonal analysis presentations and the NAFSIP presentations, countries broke into their various groups and using a template (see annex 2) that was provided before and during the workshop agreed upon the following:

### Country Led Situation Analysis:

Countries were in agreement with the proposed methodology for carrying out the country-led situational analysis. Below is a summary of issues raised during the group discussions:

Gambia:

- The proposed analysis is found to be agreeable;

- Proposed TORs content found agreeable, however there is need to amend the condition for “5 year firm expererience” to “5 year expert experience”

The Gambia team suggested that steps for identifyinga consulting Firm will be submitted to the PACA Secretariat by Week of 16th June Consultant identification. It was also suggested that the consutants will be head hunted and consiquently engaged.

Malawi:

Malawi presented its unique case whereby they already have in place the Malawi Program for Aflatoxin Contro (MAPAC) which carried out similar work as that of the situation analysis. Malawi is also in the process of developing the Food Safety and Quality Control Situation Analysis. Therefore, the PACA Secretariat is working closely with the Malawi team to establish the best way forward for the country instead of dublicating efforts that have already been exerted my Malawi and its partners.

The Malawi team offered the following lessons from the MAPAC experience in relation to the proposed methodology for the Country-led Situation Analysis:

Table 9: MAPAC Development Process in Relation to PACA Guidelines for Situation Analysis

| # | PACA Process | MAPAC |
| --- | --- | --- |
| 1 | Identify key crops | The problem was identified through the MCDA which is a framework/process that is used to identify priority SPS issues that limit exports. - Groundnuts was the main crop initially but later maize was included |
| 2 | Determine prevalence & Distribution of Aflatoxin | Desk Review |
| 3 | Characterize risk of Aflatoxin contamination & exposure along the value chain | Stakeholder Consultation (group and individual) |
| 4 | Estimating economic impact from Aflatoxin contamination | Draft Report Generated |
| 5 | Identify & prioritize opportunities for Aflatoxin control | Report Validation |
| 6 | Consultation with stakeholder to Validate findings | Opportunities and challenges – gaps identified as recommendation – see below |
|  | NB. a) The MAPC document gives the Aflatoxin situation analysis for Malawi and therefore exonerates Malawi from conducting Country led situation analysis (2.1 and 2.2) b) While the process did not necessarily follow the phases as stipulated in the PACA guidelines almost all issues as stipulated in the respective phases were captured except for issues below |  |
|  | Gaps in the MAPAC |  |
| 1 | Estimation of economic impact from Aflatoxin Contamination |  |
| 2 | Define the prevalence of Aflatoxin in the groundnut and Maize value chains and cost benefit analysis of post-harvest interventions for improved Aflatoxin control and management options |  |
| 3 | Market analysis of value addition products (groundnut oil, groundnut cake) that can be created from contaminated groundnuts: Determine optimum processing for contaminated groundnuts and conduct initial analysis of markets. |  |
| 4 | Determine the prevalence of Aflatoxin in humans |  |

Senegal:

The Senegalese team suggested the following steps for carrying out the situation analysis:

- Identify of key crops of concern

- Determine prevalence and distribution of aflatoxin

- characterize risks of aflatoxin contamination and exposure along priority value chains

- Estimate economic impact due to aflatoxin contamination

- Identify and prioritize opportunities for aflatoxin control

- Conduct stakeholder meeting and communicate, validate findings and identify priority actions

On objectives of the situation analysis Senegal suggested the following additions:

- The government of Senegal is conducting a food safety  system and aflatoxin situation analysis to set up a strategic action by identifying existing program to consolidate efforts on the main issues

- Inform the codex committee review and AfricaAIMS data submission and implementation process

- The Natiional Consulting will work closely, in addition to PACA, RECS, with relevant ministries( for Fisheries, Environnment, Livestock, Industry)

- Assess the perception on the public on aflatoxin matters

The senegalese team suggested the following timelines for major outputs of the situation analysis:

Table 10: Senegal Steps and Timelines for Situation Analysis

|  | Develop a draft detailed action plan and meet with ATWG, national food safety focal point, and other key informants to solicit comments on the draft | 30 June |
| --- | --- | --- |
|  | Attend the PACA Pilot Country Activities - 2014 Country Activities inception workshop to guide the process for AfricaAIMS data collection, submission and implementation | 15 July |
|  | Develop Conceptual Framework for country-led situational analysis and economic impact assessment | 15 July |
|  | Draft situational analysis | August |

Senegal suggested the following approach for identifying the consultants for the situation analysis and NAFSIP Review:

- make an open call for candidatures

- the ATWG will play the following roles:

  - will support the consultant

  - sensitize  decision makers and

  - promote broader public awareness

Tanzania:

The Tanzania representatives agreed on the following steps and outputs in conducting the situation analysis

- Draft review of situational analysis and Draft country CAADP situational analysis including: stakeholder mapping in the CAADP process

- Conduct consultation meetings in at least five of the identified regions and value chains

- Collect and compile new data (prevalence and exposure data) from key technical public and private sectors

- Perform economic impact assessment, including mapping map existing and planned relevant activities for aflatoxin control, food safety programs, health and nutrition monitoring programs, and value chain development programs

- Draft Country and CAADP situation analysis reports

- Map of the existing food safety systems in country and demonstrate how aflatoxin mitigation strategies can be implemented through these structures

- Identify gaps, options and interventions for food safety control emphasizing on aflatoxin prevention and control

- Identify gaps in capacity and interventions including barriers to the adoption and adaptation of recommended practices and technologies

- Map existing and planned relevant activities (e.g. activities focused on aflatoxin control, food safety programs, health and nutrition monitoring programs, value chain development programs) against the economic analysis conceptual framework as proposed in the 2012 Tanzania aflatoxin assessment

- Report of a meeting with interested stakeholder leaders and other key informants to rough out priority areas, activities and interventions, using multicriteria decision analysis, or other prioritization method

- Views of Ministries on findings and draft situational analysis and economic impact assessment report to relevant Ministries (health, trade and agriculture) at an appropriate forum

- A draft situational analysis and economic impact assessment and TAFSIP review reports submitted to PACA

Uganda:

1. The group agreed on the situation analysis steps, phases and methodologies for conducting the situation analysis as presented by Dr. Gnolonfin.

In reviewing the proposed draft ToR for Ugandan Consultant, it was advised to co-op the national taskforce on the consultancy team and involve them in the data collection exercise. Since Uganda has already identified consultants, the group discussed on how the various ministries will support the national consultants, the group suggested the following:

- Ministries, upon request will formally nominate the participating focal persons

- Ministries will work through the focal persons in the Technical Working Groups in line ministries Departments and agencies to avail and also allow to access the necessary sector data (will need a letter from PACA)

- Provide list of key stakeholders in value chains

The Government of Uganda has submitted the revised ToRs for the situation analysis to PACA Secretariat.

### NAFSIP Reviews

All 5 pilot countries were in agreement with the NAFSIP review process and steps, below are some additional suggestions from group discussions:

- Gambia:Commitment of Permanent Secretaries & Directors to be confirmed by the week of the 16th June 2014

- Malawi:Agreed to the suggested timelines and steps

- Senegal:Agreed to the suggested timelines and steps

- Tanzania:Agreed to the suggested steps and proposed new timelines as per Table 7

- Uganda: Agreed to the suggested timelines and steps for the NAFSIP reviews

### Agreed Timelines

Gambia, Malawi, Senegal and Uganda agreed to the timelines as suggested by PACA Secretariat (see figure 11). Tanzania suggested the following timelines:

Table 11: Tanzania Timelines for implementations of activities

| No. | Deliverable | Due Date (on or about) |
| --- | --- | --- |
| 1. | Attendance in the PACA Pilot Country Activities - 2014 Country Activities Inception workshop to guide the process for AfricaAIMS data collection, submission and implementation | 13 June, 2014 |
| 2. | Develop a draft detailed action plan and meet with Mycotoxin Steering Committee, national food safety focal point, and other key informants to solicit comments on the draft |  |
| 3. | Conceptual Framework for country-led situational analysis and economic impact assessment; and Conceptual Framework for TAFSIP review | 30 June, 2014 |
| 3.1 | Inform all stakeholders involved in the CAADP process in country including farmers organization, food safety task force (and all relevant task forces), donors, civil society, academia, private SMEs, etc. on the planned TAFSIP review | 15 July 2014 |
| 3.2 | Assess national CAADP documents including TAFSIP and brief the MSC and PACA Secretariat prior to review | 22 July 2014 |
| 3.3 | Review the CAADP process in country in close consultation with the CAADP Focal person and clearly demonstrate how aflatoxin mitigation can be implemented through this framework | 28 July 2014 |
| 4. | Draft review of situational analysis and Draft country CAADP situational analysis including: stakeholder mapping in the CAADP process | 30 July, 2014 |
| 4.1 | Develop a concept note, methodology and program for updating the Country situation analysis and TAFSIP review | 10 August 2014 |
| 4.2 | Create aware awareness and Conduct consultation meetings with main stakeholders at Ministry level | 15 August 2014 |
| 4.3 | Review literature and define regions and value chains according to risk of aflatoxins contamination and exposure | 17 August 2014 |
| 4.4 | Conduct consultation meetings in at least five of the identified regions and value chains | 30 September 2014 |
| 4.5 | Collect and compile new data (prevalence and exposure data) from key technical public and private sectors | 30 August 2014 |
| 4.6 | Perform economic impact assessment, including mapping map existing and planned relevant activities for aflatoxin control, food safety programs, health and nutrition monitoring programs, and value chain development programs | 10 September 2014 |
| 4.7 | Draft Country and CAADP situation analysis reports | 10 October 2014 |
| 5. | Map of the existing food safety systems in country and demonstrate how aflatoxin mitigation strategies can be implemented through these structures | 15 August, 2014 |
| 5.1 | Identify gaps, options and interventions for food safety control emphasizing on aflatoxin prevention and control | 20 August 2014 |
| 5.2 | Identify gaps in capacity and interventions including barriers to the adoption and adaptation of recommended practices and technologies | 20 August 2014 |
| 5.3 | Map existing and planned relevant activities (e.g. activities focused on aflatoxin control, food safety programs, health and nutrition monitoring programs, value chain development programs) against the economic analysis conceptual framework as proposed in the 2012 Tanzania aflatoxin assessment | 25 August 2014 |
| 6. | Report of a meeting with interested stakeholder leaders and other key informants to rough out priority areas, activities and interventions, using multicriteria decision analysis, or other prioritization method | 30 August, 2014 |
| 6.1 | Propose a date suitable to the Ministry of Agriculture Food security and cooperatives to convene a workshop for TAFSIP review | 15 September 2014 |
| 6.2 | Circulate findings from the situational analysis to all stakeholders together with relevant background documents (TAFSIP, PACA Strategy, and Regional Aflatoxin Action Plan) | 20 September 2014 |
| 6.3 | Facilitate TAFSIP review using proposed methodology | 25 September 2014 |
| 6.4 | Convene relevant stakeholders to assess whether food safety issues are addressed in the TAFSIP | 30 September 2014 |
| 6.5 | Finalise development of a National Aflatoxin Mitigation Strategy and Investment Program for the inclusion in the TAFSIP. | 20 September 2014 |
| 7. | Views of Ministries on findings and draft situational analysis and economic impact assessment report to relevant Ministries (health, trade and agriculture) at an appropriate forum | 15 September, 2014 |
| 7.1 | Propose dates for roundtable meetings with Ministry officials to provide feedback on the process | 30 September 2014 |
| 7.2 | Convene the roundtable meetings for giving feedback to government officials | 15 October 2014 |
| 8. | A draft situational analysis and economic impact assessment and TAFSIP review reports submitted to PACA | 30 September, 2014 |
| 9. | Final report on all the work conducted submitted to PACA | 30 October, 2014 |
| 10 | Presentation to the final national aflatoxin investment program that has been mainstreamed in the TAFSIP to donors and government officials for financial commitments | 30 November 2014 |

Table 10: Tanzania Suggested Timeline

## Day 2- Closing Session

The official closing session was chaired by Dr. Janet Edeme (AUC) who congratulated the delegates for successful deliberations. Dr. Edeme invited Dr. Ayalew (AUC-PACA) to address the audience. Dr. Ayalew emphasized the importance of keeping to the timelines and actions as agreed at the workshop. In conclusion, Dr. Amare encouraged participants to be ambassadors for aflatoxin mitigation within their respective organizations. Dr. Edeme called on delegate from Uganda who gave a vote of thanks to the AUC and PACA secretariat as well as the RECs and all delegates at that workshop for the organization of the workshop and attendance at the workshop respectively. Dr. Janet also called upon Dr. Zainab Jallow to offer next steps for the workshop which are reflected below:

Table 12: Next Steps

| Activity | Deadline |
| --- | --- |
| Concretely agree on the timeline | 11 June 2014 |
| Countries to submit concrete feedback on the AfricaAIMS trainees | 20 June 2014 |
| PACA Secretariat to share the workshop outcomes | 20 June 2014 |
| PACA Secretariat to share with countries a refined data collection methodology with clear data to be collected | 27 June 2014 |
| Countries to send a final capacity gap form | 20 June 2014 |
| PACA to assist countries in acquiring (as much as possible) equipment for filling the capacity gaps in key labs/ reference labs | 3 August 2014 |
| Implement country activities according to the agreed timelines proposed to countries | June – November 2014 |

In conclusion, Dr. Edeme invited Dr. Mponda from Naliendele Agricultural Research Centre, Ministry of Agriculture, Cooperatives and Food Security, Tanzania to close the session. Dr. Mponda reiterated the words of Dr Ayalew and Dr. Edeme by congratulating the delegates for the active and interactive participation. Dr. Mponda concluded by encouraging delegates to implement the actions agreed upon at the workshop.

Figure 12: Closing Session

# Workshop Participants

| PACA Inception Workshop Participants list |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sponsored List |  |  |  |  |  |  |  |
| No. | Positions |  |  |  | Sector | COUNT/ORG | Email |
| 1 | Jawara | Sana | Ministry of Health | Chief Public Health Officer | Health | Gambia | sanabairowj@yahoo.com |
| 2 | Jallow | Zainab | Food Safety and Quality Authority | Acting Director | Multi-sectoral | Gambia | zjallow@yahoo.com |
| 3 | Ndey Naffie | Ceesay | Ministry of Trade, Industry, Regional Integration & Employment | Principal Economist | Trade | Gambia | naffie ceesay (nssc79@yahoo.com) |
| 4 | L.K Darboe | Momodou | Ministry of Agriculture (NARI) | Principal Reseach Officer | Agriculture | Gambia | modoulamin darboe (mldarboe@yahoo.com) |
| 5 | Kachingwe | Daisi | Ministry of Africulture | CAADP Focal Point | Agriculture | Malawi | kachingwedk@yahoo.co.uk |
| 6 | Kamdonyo | Flora | Ministry of Health |  | Health | Malawi | fkamdonyo@yahoo.com |
| 7 | Mlotha | Helen | Ministry of Industry and Trade |  | Trade | Malawi | helenmlotha@yahoo.com |
| 8 | Gokah | Isaac | Ministry of Industry and Trade |  | Trade | Malawi | isaacb.gokah@gmail.com |
| 9 | Soko | Mischeck | Ministry of Agriculture, MAPAC/PACA ATWG | Chief Scientist - Mbumbwe Research Station | Agriculture | Malawi | misheck_soko@yahoo.com |
| 10 | Beye | Babacar | Chef du Laboratoire de mycotoxines Institut de Technologie Alimentaire | Chef du Laboratoire de mycotoxines | Agriculture | Senegal | babsbeye@gmail.com; dbeye@ita.sn |
| 11 | Senghor | Lamine | DPV- Ministry of Agriculture | Principal Plant Pathologist | Agriculture | Senegal | laminesenghor@hotmail.com |
| 12 | Dem | Ahmadou |  | Medical Doctor | Health | Senegal | adem@refer.sn |
| 13 | Ndoye | Magatte | Ministère du Commerce, de l'Entreprenariat et du Secteur Informe | Coordonnateur Régisseur du PRDCC | Trade | Senegal | bilpaco@yahoo.de |
| 14 | Sy | Abdoulaye | Bassin Arachidier Sud Agence Nationale de Conseil Agricole et Rural | Directeur de Zone | Agriculture | Senegal | 'ayesythies@yahoo.fr' |
| 15 | Diédhiou | Papa Madiallacké |  |  |  | Senegal | tpapemagatte@yahoo.fr |
| 16 | Mponda | Omary | Naliendele Agricutural Research Centre,MoA,Cooperatives and Food Security |  | Agriculture | Tanzania | mpondaomari@hotmail.com |
| 17 | Muro | Lightness | Ministry of Agriculture, Cooperatives and Food Security |  | Agriculture | Tanzania |  |
| 18 | Tarimo | Immaculate |  |  | Health | Tanzania |  |
| 19 |  |  |  |  |  | Tanzania |  |
| 20 | Kimanya | Martin | The Nelson Mandela African Institution of Science and Technology (NM-AIST) | Ag. Dean, School of Computational and Communication Science and Engineering (COCSE) | Multi-sectoral | Tanzania | martin.kimanya@nm-aist.ac.tz |
| 21 | Bambona | Alex | Ministry of Agriculture Animal Industries & Fisheries (MAAIF) | Head, Food & Nutrition | Agriculture | Uganda | alexbambona@gmail.com |
| 22 | Agaba | Edson Friday | National Drug Authority | Food Safety Coordinator | Multi-sectoral | Uganda | agabafriday@hotmail.com; agaba_friday@yahoo.co.uk |
| 23 | Baligeya | Mufumbiro Hakim | Uganda National Bureau of Standards | Ag. Head , Food and Agriculture Standards Division | Agriculture | Uganda | hakim.mufumbiro@unbs.go.ug |
| 24 | Mugisa | Tom | Ministry of Agriculture, Animal Industry and Fisheries | Programme Officer, Technical Services/ CAADP Focal Point | Agriculture | Uganda | mugisat@hotmail.com; tom.mugisa@agriculture.go.ug |
| 25 | Kaaya | Archileo | Makerere University | Head, Dept. of Food Technology & Nutrition | Multi-sectoral | Uganda | kaaya.archileo48@gmail.com |
| 26 | Bisamaza | Maria | Makerere University | Consultant and Researcher | Multi-sectoral | Uganda | maria.bisamaza@gmail.com |
| 27 | Joseph | Zafac | IAPSC | Assistant-Entomology | Multi-sectoral | Cameroon | SaniF@africa-union.org |
| 28 | Byanyima | Martha | COMESA | SPS Expert - IPPSD | Trade | Zambia | MByanyima@comesa.int |
| 29 | Wafula | David | EAC | Agriculuture Specialist | Multi-sectoral | Tanzania | dwafula@eachq.org |
| 30 | Louis | Murango | EAC | Principal Public Health&Nutrition Officer - EAC-USAID Aflatoxins and Improved Nutrition Project | multi-sectoral | Tanzania | lmurango@eachq.org |
| Resource Persons |  |  |  |  |  |  |  |
| 31 | Edeme | Janet | AUC-DREA | Head of Division, Rural Economy | Agriculuture | Ethiopia | edemej@africa-union.org |
| 32 | Ayalew | Amare | AUC - PACA Secretariat | Program Manager | Multi-sectoral | Ethiopia | Amarea@africa-union.org |
| 33 | Gnolonfin | Benoit | AUC - PACA Secretariat | Technical Officer | Multi-sectoral | Ethiopia | BenoitG@africa-union.org |
| 34 | Chunga | Wezi | AUC - PACA Secretariat | Program Officer | Multi-sectoral | Ethiopia | chungaw@africa-union.org |
| 35 | Frank Dixon | Mugyenyi | AUC-DTI | Senior Industry Advisor | Trade | Ethiopia | MugyenyiF@africa-union.org |
| 36 | Mabvuto | Kango | AUC-DSA | Ag. Head of Health, Nutrition and Population | Health | Ethiopia | KangoM@africa-union.org |
| 36 | Petros | Tigistu | AUC-Finance | Finance Officer | N/A | Ethiopia | TigistuP@africa-union.org |
| 38 | Oudreaogo | Phillippe | AU-IBAR | Information Systems Officer | Multi-sectoral | Kenya | philippe.ouedraogo@au-ibar.org |
| 39 | Stinson | Barbara | Meridian Institute | Senior Partner | Multi-sectoral | USA | bstinson@merid.org |

# Agenda

| 8:30 am -9:00 am | DAY I Registration | Time allocation (30 mins) | Chair |
| --- | --- | --- | --- |
| 9.00 am- 9:55am | Opening Session Welcome note: Dr. Janet Edeme, Head of Division, Rural Economy and Agriculture, AUC Opening remarks: - Ms. Martha Byanyima, SPS Expert - IPPSD COMESA Secretariat COMESA Secretariat - Mr. David Wafula – Agricultural Specialist East African Community, EAC Secretariat Host Country Welcome Remarks: Dr. Fabien Mkondo- Assistant Director, Plant Health Protection | (10 min) (15 min) (15 min) (15 min) | Mr. Raymond Wigenge ro – Director of Food Safety, Tanzania Food and Drugs Authority, Ministry of Health and Social Welfare |
|  | Meeting Objectives: PACA Secretariat | (5 min) |  |
| 10:00 – 10:20am | Coffee/Tea Break Group Photo | (15 min) (5 min) |  |
| 10:20 am-11:20 am | Session I: Technical Briefs: Adoption of Program PACA- Flagship program of CAADP = Dr. Janet Edeme, Head of Division, Rural Economy and Agriculture, AUC - Overview of PACA (PACA Strategy and Strategic Plan) – Dr. Amare Ayalew, Program Manager, PACA Secretariat, AUC - PACA Pilot Country Activities for 2014 – Mrs. Wezi Chunga-Sambo, Program Officer, PACA Secretariat, AUC Questions and discussions | (15 min) (15 min) (15 min) (15 min) | Ms. Martha Byanyima SPS Expert - IPPSD COMESA Secretariat |
| 11:20 am-12:30 pm | Session II: AfricaAIMS • AfricaAIMS - Importance of establishing an Africa owned information management system on aflatoxin - Mrs. Wezi Chunga-Sambo, Program Officer, PACA Secretariat, AUC - Methodology and Implementation Plan of AfricaAIMS – Mr. Benoit Gnolonfin, Technical Officer, PACA Secretariat, AUC - AU-IBAR’s ARIS II and how it works – Mr. Philippe Ouedraogo,Information Systems, AU-IBAR - Using existing structures for implementing AfricaAIMS – WHO (INFOSAN) Questions and Discussions | (10 min) (20 min) (20 min) (10 min) (10 min) | Dr. Janet Edeme, Head of Division, Rural Economy and Agriculture, AUC |
| 13:0 pm- 2:00 pm | Lunch |  |  |
| 2:00 pm-3:30 pm | Session III: Breakout Sessions Group 1: REC Group Meeting - Review of ECOWAS, EAC, and COMESA action plan plans Group 2: Parallel Member States Discussions - Mechanism for implementing the AfricaAIMS (using the draft methodology as reference) - Review of AfricaAIMS methodology to fit with country contexts - Gauge country capacity gaps for implementing AfricaAIMS - Propose candidates to be trained in AfricaAIMS data submission in country | (120 min) | Dr. Janet Edeme, Head of Division, Rural Economy and Agriculture, AUC Supported by PACA- AUC Secretariat |
| 3:30 pm-3:45 pm | Tea/coffee | 15 min |  |
| 3:45pm – 5:00pm | Session IV: Continue Breakout session discussions until the end of the day | (75 min) |  |
|  | Day II |  |  |
| 9:00 am-9:10 am | Recap of Day 1 Mr. Daisi kachingwe, CAADP Focal Point, Ministry of Agriculture and Food Security, Malawi | 10 min | Dr. Janet Edeme, Head of Division, Rural Economy and Agriculture, AUC |
| 9:10 – 10:40 | Country and RECs report from breakout sessions (Plenary Session) - REC s presentation Questions Country Presentations - Gambia Questions - Senegal Questions - Malawi Questions - Uganda Questions - Tanzania Questions | (10 min) (5 min) (10 min) (5 min) (10 min) (5 min) (10 min) (5 min) (10 min) (5 min) (10 min) (5 min) | Senegal Dr. Louis Murango - Principal Public Health&Nutrition Officer - EAC-USAID Aflatoxins and Improved Nutrition Project |
| 10:40am- 11:00am | Coffee/ tea break | (30 min) |  |
| 11:00 am -11:45 11:45 – 12:30pm | Launch of PACA Website - Introduction and Online Demonstrations - Dr. Amare Ayalew, Program Manager, PACA Secretariat, AUC Questions and discussions Country-led situational analysis Sharing lessons with past methodologies used for country analysis --- (PPT) Dr. Martin Kimanya, Ag. Dean School of Computational and Communication Science and Engineering (COCSE) Proposed methodologies and steps for Situation Analysis – Dr. Benoit Gnolonfin, Technical Officer, PACA Secretariat, AUC Questions and Answers | (10 min) (20 min) (150 min) (20 min) (10 min) (10 min) | Archileo Kaaya, Head, Dept. of Food Technology & Nutrition, Makerere University Dr. Janet Edeme, Head of Division, Rural Economy and Agriculture, AUC Facilitated by PACA- AUC Secretariat |
| 12:30 – 1:30 pm | Lunch | (60 min) |  |
| 1:30 am -2:45pm | Country-led situational analysis (cont…) Expected outcomes of Group Discussions - Dr. Janet Edeme, Head of Division, Rural Economy and Agriculture, AUC Guided Group Discussions Available country capacity for aflatoxin policy reviews and analysis - ATWG and their role in facilitating country activities | (5 min) (70 min) |  |
| 2:45pm- 3: 35pm | NAFSIP Reviews Proposed methodology/steps for NAFSIP reviews (PPT) – Mrs. Wezi Chunga- Sambo, Program Officer, PACA Secretariat, AUC Group discussions | (50 mins) | Dr. Janet Edeme, Head of Division, Rural Economy and Agriculture, AUC |
| 3:35.pm-3.50 pm | Tea | (15 min) |  |
| 3:50 pm -4:45 pm | Presentation on Proposed timeline for agreed country activities - Mrs. Wezi Chunga-Sambo, Program Officer, PACA Secretariat, AUC Country Group Breakout Sessions – Discusss and amend proposed timeline for implementing activities (with names of responsible persons) | (10 min) (45 min) | Dr. Janet Edeme, Head of Division, Rural Economy and Agriculture, AUC |
| 4:45 pm -5:35 pm | Plenary Presentation of agreed timelines and next steps Uganda Senegal Malawi Uganda Tanzania | (10 mn) (10 min) (10 min) (10 min) (10min) | Ms. Martha Byanyima SPS Expert - IPPSD COMESA Secretariat |
| 5:35pm-5:450pm | Wrap up and logistics | (15 min) | Gambia |

# Annexes

## Annex 1: AfricaAIMS Parallel Breakout Session Template

Kindly use the following worksheet to guide discussions in your working group and record the outcomes from your discussion.  It is fine to extend your conversation beyond the topics proposed below.

The following documents are available for reference to support your discussions:

- Africa Aflatoxin Information Management System (AfricaAIMS)Draft Methodology

- PACA- pilot country laboratory capacity for aflatoxin testing and diagnosis

- Country Training Selection Guide

- Country Lab Capacity Form

- AfricaAIMS selection guideline for Country trainees

1:30 – 3:30pm

INTRODUCTIONS (5 minutes)

Please list the members of your working group and sector that each is affiliated to (health, trade/agriculture).

Section 1a.Mechanisms for implementing the AfricaAIMS in Country

The AfricaAIMS draft methodology has identified the following data to be collected in country:

| Health | Trade | Agriculture |
| --- | --- | --- |
| Liver cancer | Aflatoxin standards in countries | Production levels |
| Aflatoxin levels in humans / bio-marker data (blood and/ urine) | Volume of export and imports | Aflatoxin contamination along the value chain (prevalence and levels) |
| Extent of consumption of aflatoxin prone crops (maize, groundnut, etc.) | Export rejections | Seed moisture content |
| Rate of childhood stunting (Diarrhea: presence of Cryptosporidium parvum, Giardia lamblia and EnteroaggregativeEscherichia coli); body weight, height. | Existence of free trade areas/ border control | Drying, storage, processing and packaging, storage |
| Others (HIV, HBV, Nodding Disease, etc.) |  | Aflatoxin control interventions |

- In your expert opinion, which of this data do you think can be collected in country and which ones cannot?

- Are there any data you think are important to be collected that have not been included in table 1? If so, list the data.

Based on the data you have identified as suitable for collection in your country, answer the following:

- Who will collect the data you have identified and why do you think they are well placed in your country to collect this data?

Examples can include: Farmers organizations, processors associations, agriculture and health extensions services, regulatory bodies, research institutions, private sector, NGOs, etc. (give specific names of the respective entities)

- Where applicable, who will analyze the samples for aflatoxin content and why do you think they are well placed in your country to analyze this data?

Examples can include: Competent private laboratories, research institutions, farmers’ organization national laboratories (give specific names of the respective entities)

- In your group, map out the data submission process and clearly identify which institution or organization in your country will be responsible for data submission in the three sectors (health, trade, agriculture) to a central focal point for submission into AfricaAIMS.

Examples: e.g. Agriculture sector – National Research Stations? Health - Central Hospitals/Clinics? Trade – INFOSAN focal points?

- In your group discuss who you think is the appropriate body/institution to be re responsible for data verification and submission at country level as an AfricaAIMS focal point?

Examples: e.g. Tanzania Food and Drugs Administration (Ministry of Health), Tanzania; Malawi Program for Aflatoxin Control - MAPAC (Ministry of Trade), Malawi; Aflatoxin Management Committee (Ministry of Trade), Uganda.

- In your group, identify the main agro-ecological zones for production of main value chains (maize, groundnut). You may include animal feed (poultry, fish)

Section 1b.Capacity Needs for Implementing AfricaAIMS in country

- Gauge country capacity gaps for implementing AfricaAIMS

Using the country lab capacity form, list:

- Equipment necessary for collecting and analysing data a identified in section 1a

- Human capacity needs for analysing data, collecting and or entering data for AfricaAIMS

- Propose candidates to be trained in AfricaAIMS data submission in country

Using the AfricaAIMS selection guideline for Country trainees, in your groups, agree on a total of 10 people that should be trained from your country for data collection, analysis and submission

## Annex 2: Situational Analysis, NAFSIP Reviews and timelines -Parallel Breakout Session Template

Kindly use the following worksheet to guide discussions in your working group and record the outcomes from your discussion.  It is fine to extend your conversation beyond the topics proposed below.

The following documents are available for reference to support your discussions:

- TORs - Country Situation Analysis

- TORSs - Country NAFSIP Reviews

- Proposed timeline for agreed country activities

11:00 – 12:10pm

Section 1a. Country Situational Analysis

- Based on the PPT presentation given by PACA Secretariat on proposed phases and steps for country-led situational analysis, review and discuss in your group if this is an agreeable proposal and amend if necessary.

- Review the proposed country-specific draft TORs for national consultant conducting Situational Analysis and refine based on country needs

- For countries that have already identified consultants to carry out the analysis (Tanzania and Uganda):

- Detail how the various ministries will support national consultants in carrying out the work.

- Agree on the role of ATWGs in carrying out the situation analysis

- For countries that have not selected a consultant to carry out the situation analysis (Gambia, Malawi and Senegal),

- Detail out ways of identifying and engaging consultant

- Agree on the role of ATWGs in carrying out the situation analysis

12:20- 12:30pm

Section 1b.NAFSIP Reviews

Based on the PPT presentation given by PACA Secretariat on proposed steps and timeline for NAFSIP reviews discuss in your group if this is an agreeable proposal and amend if necessary to suit country specific needs.

1:45- 3:05pm

Section 1c. Proposed timeline for agreed country activities

Using the country specific proposed timeline sheet:

- Discuss and amend the suggested timelines for implementing activities to suit country specific needs

- List names of people in your group to take lead in each of the identified activities and steps.

## Annex 3: Regional Economic Communities Breakout Session Template

Kindly use the following format to guide discussions in your working group and record the outcomes from your discussion.  It is fine to extend your conversation beyond the topics proposed below.

The following documents are available for reference to support your discussions:

- Regional action plans

- Draft COMESA scoping study report?

- STDF PPG application

- 2014/15 PACA Work Plan

1:30 – 3:30pm

INTRODUCTIONS (5 minutes)

Please list the members of your working group.

Regional Aflatoxin/Food Safety Action Plans (40 minutes)

Share the status of aflatoxin action planning in your region, what has or is working well, what could be improved, and any suggestions you have for other regions based on your experience.

Identification of REC-PACA Joint Activities (40 min)

From your respective focus areas and work plans at REC level and having looked at the PACA 2014/15 work plan and strategy, please suggest areas of mutual interest and collaboration for 2014/2015. Any suggestions for the out years (2016-17)?

Policy and Regulatory Landscape (20 min)

Review and discuss the approach to and findings from the policy and regulatory scoping study recently conducted in the COMESA region.  PACA is interested in expanding this study to ECOWAS, SADC and EAC Member States.  Discuss how this can best be accomplished (i.e. can the RECs provide names and contact information for food safety focal points or SPS authorities in countries?).

Financing of Aflatoxin Situation Analysis and Action Plans (20 minutes)

Review and discuss STDF Project Planning Grant and Project Grant opportunities, as well as other funding sources for aflatoxin situation and food control system analysis and action planning.

How can you support one or more of the 2015 pilot countries in your region to apply for a PPG to conduct a country-led aflatoxin situation analysis (due 18 July)? What lead role can your REC be playing in an application for a regional project which makes the link between the country-level work and the regional aflatoxin action plans? Or propose how country / regional level plans could be linked to, and mainstreamed into, broader trade capacity building programmes (Aid for Trade, EIF, etc.)?

3:45 – 5:00 pm

NAFSIP Reviews (20 minutes)

What suggestions do you have for PACA to successfully work with RECs and countries to conduct NAFSIP reviews?

AfricaAIMS (15 minutes)

What suggestions do you have for PACA to successfully work with RECs and countries to implement AfricaAIMS?

Next Steps (20 minutes)

Review the 2015 PACA Work Plan and identify intervention areas that your REC would like to invest in in 2015.

## Annex 4: PACA- pilot country laboratory capacity for aflatoxin testing and diagnosis

Table 1. Country laboratory capacity to perform aflatoxin analysis within the food safety and surveillance systems

Name of country: ______________________________________________

Any accredited laboratory ___________________________________________

Inspection services mechanism and ministry in charge: domestic, regional and international levels ___________________________________________________________

| Location of the lab (organization and address) | Laboratory support service with focus on aflatoxin |  |  |  |  |  |  |  | Capability to support local, regional and international trade |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Type of equipment and age | Maintenance of the equipment | Accessibility to reagents and consumables | Supplier of reagents and consumables | Method (s) used and validated SOP in place | Types of food and number of samples analysed for aflatoxin during the past 3 years | Range of aflatoxin levels (ppb) | Number of technicians trained |  |

Table 2. Country laboratory capacity to diagnose health related aflatoxin diseases including liver cancer, childhood stunting, levels in human blood or urine/biomarker, HIV, HBV, nodding diseases

2.1. Liver cancer: jaundice as nonspecific symptom of liver damage

| Mechanism and ministry/department in charge | Equipment and age | Maintenance of the equipment(services provider | Accessibility to reagents and consumables | Supplier of reagents and consumables | Techniques used | Validated SOP in place | Number of trained technicians | Nber of patients/ year | Nber of +ve patients |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

2.2 Other diseases: HIV, HBV, Nodding syndrome

| Mechanism and ministry/department in charge | Equipment and age | Maintenance of the equipment(services provider | Accessibility to reagents and consumables | Supplier of reagents and consumables | Techniques used | Validated SOP in place | Number of trained technicians | Nber of patients/ year | Nber of +ve patients |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

2.3 Aflatoxin in levels in human/urine: Lysine albumin adduct-biomarker

| Mechanism and ministry/department in charge | Equipment and age | Maintenance of the equipment(services provider | Accessibility to reagents and consumables | Supplier of reagents and consumables | Techniques use | Validated SOP in place | Nber of trained technicians | Nber of patients/ year | Nber of +ve patients | Range of aflatoxin level (ng/µl) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

2.4 Childhood stunting: age < 5 years

| Equipment/instrument and age | Maintenance of the equipment(services provider | Accessibility to reagents and consumables | Supplier of reagents and consumables | Techniques used | Validated SOP in place | Nber of trained technicians | Epidemiology and prevalence |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Nber patients/year | Nber +ve patients | Precence of C. parvum1 | Precence of G. lamblia2 | Presence of EAggEC3 | Body weight | Height | Average stunting prevalence |

1. Cryptosporidium parvum; 2. Giardia lamblia; 3.EnteroaggregativeEscherichia coli.

## Annex 5: AfricaAIMS selection guideline for Country trainees

In 2014, PACA will train 10 people per Pilot country in 3 sectors (health trade and agriculture) for data collection, analysis and submission on AfricaAIMS. The following criteria should be used in suggesting names to be trained in country.

Bearing in mind the suggested data required for submission on AfricaAIMS (listed in table 1 below), suggest names that have access to or can collect, analyze and submit such data.

| Health | Trade | Agriculture |
| --- | --- | --- |
| Liver cancer | Aflatoxin standards in countries | Production levels |
| Aflatoxin levels in humans / bio-marker data (blood and/ urine) | Volume of export and imports | Aflatoxin contamination along the value chain (prevalence and levels) |
| Extent of consumption of aflatoxin prone crops (maize, groundnut, etc.) | Export rejections | Seed moisture content |
| Rate of childhood stunting (Diarrhea: presence of Cryptosporidium parvum, Giardia lamblia and EnteroaggregativeEscherichia coli); body weight, height. | Existence of free trade areas/ border control | Drying, storage, processing and packaging, storage |
| Others (HIV, HBV, Nodding Disease, etc.) |  | Aflatoxin control interventions |

Trainnee Profile

- Must be employed in a recognized institution in country

- Must be in a middle management or management position

- Must be willing to train others (at least 3 other people) from the training they receive from PACA

- Must have basic competent knowledge in excel

- Must have some knowledge of PACA and or aflatoxin

- Must be willing to allocate at least 2 hours a month on data analysis, entry and submission on AfricaAIMS

Representation of Trainnees

- 2 delegates from trade (at least 1 delegate should be selected who has access to data on export/import rejection due to aflatoxin levels)

- 2 delegates from health (preferably medical doctors in central government)

- 3 delegates from agriculture (at sub-regional, regional and national level)

- 1 delegate from bureau of standards/ food safety authority/ food and drug administration/ competent authority

- 2 delegates from reference labs

- At least 40 or more percent of trainees should be women

- Where possible, at least 1 of the trainees should be a student or research fellow (if applicable)

- At least 1 of the trainees (regardless of sector) should be part of the ATWG

## Annex 6: Africa Union Speech (Opening Session)

| #### AFRICAN UNION |  | #### UNION AFRICAINE |
| --- | --- | --- |
|  |  | #### UNIÃO AFRICANA |
| ##### Addis Ababa, ETHIOPIA P. O. Box 3243 Telephone 517 700 Cables: OAU, ADDIS ABABA |  |  |

STATEMENT

DELIVERED BY

Dr Janet Edeme,

HEAD, RURAL ECONOMY

AFRICAN UNION COMMISSION

AT THE

Inception Workhshop on PACA Pilot Country Activities-2014

Kunduchi Hotel

10-11 June 2014

Dar es Salaam, Tanzania

10 JUNE 2014

- Distinguished Guests

- Representatives of African Member States The Gambia, Malawi, Senegal, Tanzania,  and Uganda

- Representatives of Regional Economic Communities

- Representatives of other African Institutions

- Other invited Guests

Ladies and Gentlemen

I present to you the warm compliments from H.E Commissioner Rhoda Peach Tumusiime and her best wishes for the progressive efforts on the institutionalization of the Partnership for Aflatoxin Control in Africa (PACA) in the African farming systems.

I extend the warm greetings from the Chairperson of the PACA Steering Committee, Dr. Abebe Haile Gabriel, who, together with the full PACA Steering Committee have continued to provide the leadership and strategic guidance that the continent requires at this time on mitigating aflatoxins in Africa.

It is with a great sense of appreciation that I, on behalf of the PACA, welcome you all to the very warm and peaceful ambience of the city of Dar es Salaam.  In particular we present our warm compliments and appreciation to H.E Jakaya Kikwete, his government and the people of Tanzania for granting the hosting rights, the enabling environment and the warm reception and hospitality since our arrival in this beautiful country.

At this juncture, we would like to commend the efforts of the government of Tanzania for co-hosting this crucial workshop. I will also like to recognize the presence and support of our key partners from Nelson Mandela-African Institute for Science and Technology who were key in preparing for this workshop.

We see this Inception Workshop on the PACA Pilot Country Activities as a critical step in the partnership with Member States to take direct action to reduce aflatoxin exposure to our people. In line with its Mid-Term Strategic Plan (2014-2017), PACA will, in 2014, initiate three major activities in five pilot countries. The activities are:

- Establish Africa Aflatoxin Information Management System (AfricaAIMS);

- Support country-led aflatoxin situation analysis and action plan;

- Mainstream aflatoxin control through the PACA initiative in CAADP National Agriculture and Food Security Investment Plans (NAFSIPs).

This workshop is a clear testimony to the seriousness African leaders attach to safeguarding consumer health, supporting agricultural development, and facilitating trade by catalyzing, coordinating and increasing effective aflatoxin control along agricultural value chains in Africa. This workshop aims to

- Sensitize pilot countries on the activities planned for in 2014 and kick-start the implementation process;

- Agree on the methodology for the implementation of the Africa Aflatoxin Information Management System (AfricaAIMS); and

- Agree on a timeline for the implementation of Pilot Country activities.

Distinguished Guests, Ladies And Gentlemen

One of the major challenges in mitigating aflatoxin in Africa is the lack of adequate information and harmonized data collection on the subject. Yet information is needed to inform policy and interventions; inform prioritization of resource allocation; promote country capacity and awareness on the aflatoxin issue. Through the PACA initiative, the African Union Commission will establish an Africa Aflatoxin Information Management System (AfricaAIMS) that will serve

as a “one stop shop” information harbor for aflatoxin information in the health, trade and agriculture sectors. Data on the AfricaAIMS will be “home-grown” owned by AU Member States and respective Regional Economic Communities (RECs). The information on the AfricaAIMS will serve policy makers, regulatory bodies, potential investors, technical agencies (health, trade and agriculture), researchers, farmers, civil society organizations (CSOs), nongovernmental

organizations (NGOs), private sector partners along the value chain and other

interested parties.

Through the Pilot Countries initiative, PACA will assist countries as they create empirical evidence on existing aflatoxin prevalence, legislation, policy and regulation, management practices and other existing control

mechanisms that can effectively inform interventions. PACA will work with locally-based consultants and Aflatoxin Technical Working Groups to conduct the analyses in alignment with the guidance of the political and technical leadership of the country.

Distinguished Guests, Ladies And Gentlemen

Aflatoxin thus poses a threat to international trade, health, food security and many other international development efforts. In our quest of attaining the laudable goal of a food-secure Africa, the political leadership of the continent endorsed the Comprehensive African Agricultural Development Programme (CAADP).  Within the last decade, Africa has chosen to take its common destiny in its own hands with a reaffirmation of commitment to increase agricultural production, productivity, food and nutrition security thereby combating hunger, malnutrition and poverty, and, indeed, contributing to the attainment of Millennium Development Goals (MDGS). Through PACA’s partnership with pilot countries, Member States will review their National Agriculture and Food Security Investment Plans, and identify opportunities where aflatoxin mitigation strategies can help achieve national goals related to agricultural productivity, trade, and public health.  Through this process aflatoxin control will be mainstreamed in national agricultural investment plans to achieve the vision of an Africa without the harmful effects of aflatoxins.

In addition to mainstreaming aflatoxin in major agricultural frameworks such as CAADP, I encourage similar efforts to be undertaken in other relevant health, trade and environmental frameworks at national and regional level, including national food safety laws and regulations. We will need to work together to strengthen surveillance, epidemiology and information sharing and communication strategies.

The PACA, through a consultative workshop held in Dar Es Salaam in April, 2013 developed its 10 year strategy (2013-2022). The strategy identifies 5 thematic areas which together provide a holistic approach to mitigating aflatoxins on the continent. These thematic areas include:

- Theme 1: Research and technology for prevention and control of aflatoxins

- Theme 2: Policies, legislation, and standards for the management of aflatoxins

- Theme 3: Growing commerce and trade and protecting human health from aflatoxins

- Theme 4: Enhancing capacity for effective aflatoxin prevention and control

- Theme 5: Public awareness, advocacy, and communication

Through its 10 year strategy, PACA aims to provide consistent coordination and coherent leadership to the continental efforts on aflatoxin control. It aims at supporting adoption of proven solutions, and identifying new ones, that will work to mitigate the impacts of aflatoxin on food security and agriculture, trade, and health in Africa. Many actors are involved in developing comprehensive solutions to control aflatoxin along the value chain, from crop production through processing and food preparation to consumption. Through participation in the PACA Pilot Country Initiative, Member States will build capacity for food safety monitoring and surveillance, document the afaltoxin situation in their country, prioritize aflatoxin mitigation actions for investment, and identify opportunities to align aflatoxin interventions with country priorities.  It is expected that these pilot countries will learn valuable lessons, and we would like to request national governments of the PACA pilot countries to avail their experiences to other countries elsewhere in Africa in order to accelerate efforts to reduce aflatoxin contamination across the continent.

Distinguished guests, ladies and gentlemen, this Inception workshop is a milestone for aflatoxin control in Africa.  We look forward to working with you in the coming year.

I wish you fruitful discussions over the next two days.

## Annex 7: EAC Speech

Logo EAST AFRICAN COMMUNITY # OPENING REMARKS INCEPTION WORKSHOP ON PACA COUNTRY ACTIVITIES 2014 10th – 11h, June , 2014 Dar es Salaam, Tanzania Delivered by Hon. Jesca Eriyo Deputy Secretary General (Productive and Social Sectors) EAC SECRETARIAT Arusha, Tanzania June, 2014

- Representative from the African Union- Dr.  Janet Edeme;

- Representative from COMESA- Ms Martha Byanyima;

- Program Manager PACA Secretariat;

- Dinstinguished participants from Gambia, Malawi, Senegal, Uganda and the United Republic of Tanzania;

- Ladies and Gentlemen;

Good morning!

On behalf of Hon. Jesca Eriyo, the EAC Deputy Secretary General in-Charge of Productive and Social Sectors, the EAC Secretariat is pleased and delighted to join you this morning.  Allow me to express my profound gratitude to the African Union and in Particular the PACA Secretariat for extending invitation to the EAC Secretariat to participate in this important inception workshop.  I wish to acknowledge the presence of everyone here.  Your attendance demonstrates the commitment and importance that you have placed on aflatoxin challenges in Africa.

Ladies and Gentlemen

The East African Community (EAC) is the regional intergovernmental organisation of the Republics of Burundi, Kenya, Rwanda, the United Republic of Tanzania, and the Republic of Uganda, with its headquarters in Arusha, Tanzania. The region has a combined population of   about 135 million people and Gross Domestic Product of $84.billion.

The EAC aims at widening and deepening co-operation among the Partner States in, among others, political, economic and social fields for their mutual benefit. The regional integration process is at a high pitch. The EAC countries established a Customs Union in 2005 and a Common Market in 2010. The Monetary Union Protocol was signed in November 2013. The next phase of the integration will see the bloc ultimately become a Political Federation of the East African States.

Ladies and Gentlemen,

The EAC Secretariat wishes to congratulate the Republics of Gambia, Malawi, Senegal, Uganda and the United Republic of Tanzania for being selected as PACA Pilot countries.  As Pilot countries, you will be expected to play pragmatic and catalytic roles in providing valuable insights and feedback on the degree of success in implementing activities spearheaded by PACA.

We urge the selected countries to seize the opportunity presented by PACA and provide a model that can replicated in other African countries. It should be noted that an enabling and facilitative policy environment will be crucial to support PACA-led efforts in the Pilot countries. Ensuring inclusive participation of all key stakeholders will be crucial for successful implementation and sustainability of the project. The need to for sustained political will and commitment from our governments is another fundamental issue.  We need to persistently remind our policy makers about the magnitude of aflatoxin in our region and the opportunities presented by PACA led interventions.  The importance of sharing information to inform evidence-based decision-making cannot be overstated. It is gratifying that this will be augmented through the establishment of Africa Aflatoxin Information Management System (AfricaAIMS).

Ladies and Gentlemen

Mainstreaming of Aflatoxin agenda in the national CAADP Compacts and Investment Plans is of strategic value to ensure that they receive the desired priority and attention. The EAC has made progress in the development of a regional CAADP Compact.  The Compact is ready for national and regional level validation. This will present opportunities to discuss further and integrate issues of aflatoxin.

Ladies and Gentlemen,

The EAC regional integration instruments including the EAC Treaty; EAC Development Strategy; EAC Common Market Protocol, EAC Customs Union, EAC Food Security Action Plan have adequately addressed issues around SPS measures.  The EAC Treaty, the Customs Union,  and the Common Market Protocol provide for the Partner States to harmonize SPS measures in order to facilitate trade within the community and other trading partners.

In 2013, the EAC Partner States adopted the SPS Protocol. The principal objective of the SPS Protocol is to adopt and enforce sanitary and phytosanitary measures in order to address safety considerations and mitigate market access barriers related to the same.  It should be noted that issues of aflatoxin are well entrenched within the broader context of the SPS Protocol.

Ladies and Gentlemen,

The EAC Council of Ministers has taken cognizance of the unprecedented threat aflatoxin poses to health, trade and food security in the region. In cognizance of the magnitude and impacts of Aflatoxin,  the EAC 27th Council of Ministers meeting held in 2013, directed the EAC Secretariat to design and implement a regional project aimed at preventing and controlling adverse impacts of Aflatoxin along the food and feed value chains.  With the support of USAID, Regional Office for East Africa, the Secretariat has moved with speed to prioritize and address the directive of the Council of Ministers.  The EAC Aflatoxin Project is one of our flagship projects designed to address the multi-faceted impacts and effects of afltoxin.  An inception workshop for the project was held in March, 2014 in the Republic of Burundi.  It should be noted that PACA team participated actively and contributed towards the success of the workshop.

One of the key outputs of the project on Aflatoxin will be development of EAC Regional Policy on Aflatoxin abatement. EAC is working closely with the International Institute of Tropical Agriculture (IITA) as a collaborating partner.  IITA is responsible for the development of technical papers and policy briefs that will inform the formulation of an evidence-based EAC Regional Policy on Aflatoxins abatement. Technical papers are being prepared in the areas of standards for food and feed, impacts on human and animal health, biocontrol and post-harvest handling, alternative uses and disposal systems, economic impact on trade and a communication strategy.

Ladies and Gentlemen,

It is important to mention that the focus of the EAC Aflatoxin project and the PACA thematic areas are complementary and mutually supportive.

Ladies and Gentlemen,

The EAC Secretariat has also finalized on regional post-harvest handling and storage measures for aflatoxins abatement in cereals, root crops, tree and oil crops and beverages. The document also contains guidelines for disposal of agricultural products that are highly contaminated with aflatoxin. The objectives of EAC regional post-harvest handling and storage measures for aflatoxin abatement are to;

- support Partner States implement integrated systems of post-harvest handling, storage and processing methods to minimize aflatoxin contamination; and

- improve knowledge of local scientists, farmers, storage operators,   processors, distributors and consumers about aflatoxin prevention and control measures.

Ladies and Gentlemen

The EAC Secretariat wishes to re-affirm our commitment to support, engage in and contribute towards implementation of interventions led PACA.  With these many remarks, I wish you all fruitful deliberations and look forward to successful implementation of the PACA Strategic Plan.

## Annex 8: The East African Community Regional Aflatoxin Project

PROJECT BRIEF- JUNE 2014

Introduction

The East African Community Partner States have accorded priority to the realization of the Millennium Development Goals of reducing by half the number of people suffering from hunger by the year 2015. While this effort requires a significant increase in the abundance and quality of food produced, food safety issues resulting from aflatoxin contamination present a number of formidable challenges.  Aflatoxins pose adverse health and economic effects along the food production and supply value chain. In particular, Aflatoxins undermine efforts to   improve nutrition, enhance agricultural production and minimizes economic gains from agricultural products, especially for small scale farmers.

Aflatoxin contamination is not adequately and appropriately controlled or regulated within the EAC region as most of food stuffs are produced and consumed locally with no or limited testing by the  relevant regulatory authorities.  As a result, millions of people living in the East Africa region consume high, unsafe levels of aflatoxin through their diets on a daily basis.

Background

The 27th Meeting of the EAC Council of Ministers called for a holistic and multi-sectoral approach that encompasses Agriculture, Health, Trade and Industry sectors in the implementation of the EAC Aflatoxin interventions at national and regional levels.  The 27th Council of Ministers further directed the EAC Sectoral Council on Agriculture and Food Security to co-opt and engage relevant experts from health, trade and industry sectors when addressing matters of aflatoxins (EAC/CM 27/Directive 21). Subsequently, the 6th Sectoral Council of Agriculture and Food Security directed the EAC Secretariat to constitute a Regional Experts Working Group on Aflatoxin (REWGA).

Pursuant to the Directives of the 27th Meeting of Council of Ministers held in August 2013, the EAC Secretariat is spearheading implementation of a regional project aimed at preventing and controlling adverse impacts of Aflatoxin along the food and feed value chains in the EAC region. The Multi-Regional Aflatoxin Abatement Project (MRAAP) is implemented by EAC with financial support from the United States Agency for International Development (USAID), Regional Office for East Africa. The main expected output from the project will be an   overarching EAC Regional Policy on Aflatoxins abatement.  The EAC Secretariat is working closely with the International Institute of Tropical Agriculture (IITA) as a collaborating partner responsible for technical backstopping. IITA is one of the 14 International Agricultural Research Centers under the Consultative Group on International Agricultural Research (CGIAR).  The Institute is currently spearheading implementation of Aflatoxin biological control programs (Aflasafe) at the national level in various African countries. IITA will be responsible for developing technical papers and policy briefs that will inform the development of an evidence-based EAC Regional Policy on Aflatoxins abatement. Technical papers will be generated in the areas of standards for food and feed, impacts on human and animal health, biocontrol and post-harvest handling, alternative uses and disposal systems, economic impact on trade and a communication strategy.

EAC will be responsible for organizing cluster meetings of experts to validate the papers developed and subsequently national and regional workshops to validate the draft policy and implementation framework.

Why a regional approach ?

Efforts at the Regional level remain fragmented and not adequately supported- technically and financially. The EAC Regional Project on Aflatoxin will give a multi-sectoral strategic and pragmatic direction- policy development and subsequently robust implementation mechanisms. The policy will be the foundation to move the EAC Partner States to a coordinated and harmonized course of action.

The objectives of the project are

- Development of EAC Regional Policy on Prevention and Control of Aflatoxins

- Establish the foundation for a Regional Bio-control Program in the EAC

- Build Capacity of the region on Aflatoxins Control and Prevention in the Region

- Build Capacity of the region on Aflatoxins Control and Prevention in the Region

Expected results

- Regional policy and implementation strategy on control of Aflatoxins control in the EAC developed,

- Foundation for Bio-control interventions in the EAC region laid, supported and implemented

- Capacities on Aflatoxins control in the region enhanced

- Awareness creation on Aflatoxins control in the region adequately conducted.

PROGRESS TO DATE

- EAC Aflatoxin Project inception workshop was held in March 2014 in Burundi.

The main objective of the inception workshop is to introduce to key Stakeholders the components and implementation arrangements of the EAC Regional Project on Aflatoxins and constitute the EAC Regional Experts Working Group on Aflatoxins (REWGA).  The Terms of reference for REWGA were presented, discussed and adopted The REWGA was constituted in accordance with the Directive (EAC/CM27/Directive 21) of the Council of Ministers. The Regional Experts Working Group on Aflatoxins (REWGA) is mandated to provide technical and advisory guidance to EAC Sectoral Council on Agriculture and Food Security and key stakeholders in the region on prevention and control of aflatoxin in the EAC region. REWGA will work at a regional level to provide leadership for coordinating and

monitoring strategic interventions on aflatoxin control.

Composition of REWGA

REWGA comprising of key representatives from: Public Health, Environment, the Food, Crops and Animal value chains. REWGA will be responsible for: supporting the agricultural development, safeguard consumer health and facilitate trade by catalyzing , coordinating and promoting effective aflatoxin control along all agricultural value chains in East Africa.

- Communication strategy Planning workshop

A planning workshop involving EAC Secretariat, IITA and EAC Partner States was held in Zanzibar from 2-3 June to lay ground for the development of a 5 year communication strategy. The communication strategy will be a robust and proactive tool to support the objectives of the EACs aflatoxin abatement program in a harmonized and consistent manner.  Specifically, the communication strategy will contribute towards heightening the level of awareness by appropriate targeting and packaging of information to inform implementation of MRAAP, convey the required feedback, and ensure the desired degree of visibility and credibility.

- Drafting of Technical Papers to inform EAC Aflatoxin Policy Formulation

TORs for each TP are specific and detailed.  TPs focus on:

- Establishing a scientific knowledge base

- Situational analysis of existing regional information

- Current status and interventions  in context of EAC

- Discussion  on appropriateness of existing interventions and identification of gaps

- Policy recommendations to inform development of EAC Regional Policy

CLUSTERS OF TECHNICAL PAPERS UNDER DEVELOPMENT

| CLUSTERS | TECHNICAL PAPERS |
| --- | --- |
| Cluster 1: Standards Development | 1. Standards for Feed |
|  | 2. Standards for Food |
| Cluster 2: Animal and Human Health | 1. Impacts on Human health |
|  | 2. Mycotoxins and the 1,000 days |
|  | 3. Impacts on Animal Health |
| Cluster 3: Agriculture | 1. Bio control |
|  | 2.Post-Harvest handling |
| Cluster 4: Environment | 1. Alternative uses |
|  | 2. Disposal systems |
| Cluster 5: Economic Impact on Trade | Global, Regional, national, on farm etc. |
| Cluster 6: Communications strategy/Mycotoxin awareness | Different target groups –Policy makers, farmers, private, public, producers, processors, consumers etc. |
| Cluster 7: Vaccinations/Immunization, Adoption of Hepatitis A&B Vaccination |  |

The following draft technical papers have been developed

- Impacts of Aflatoxin on animal health

- Impacts of Aflatoxin on human health

- Aflatoxin and 1000 days

- Standards for food and feed

The EAC Secretariat in collaboration with IITA will convene meetings of experts to review the technical papers from 16-27 June, 2014

Validation workshops will

- Discuss and verify the contents of the technical papers

- Obtain feedback and additional information

- The TPs will be revised and finalized after each verification workshop

- After all the validation workshops –the process of drafting EAC policy will commence

Indicative Project Timelines

June- December 2014

- Development and Verification of Technical Papers

Jan- June 2015

- Development and validation of the draft EAC Policy on Aflatoxin

June- December 2015

- Presentation of the draft policy to EAC Policy Organs for consideration

- Development of the Policy implementation strategy

- The EAC Regional Post-Harvest Handling and Storage Measures for Aflatoxin Abatement

The EAC Regional Post-Harvest Handling and Storage Measures for Aflatoxin Abatement has been developed through a series of technical meetings involving experts from the EAC Partner States. The main objectives of EAC draft regional post-harvest handling and storage measures for aflatoxin abatement are to;

- Support Partner States implement integrated systems of post-harvest handling, storage and processing methods to minimize aflatoxin contamination; and

- Improve knowledge of local scientists, farmers, storage operators,   processors, distributors and consumers about aflatoxin prevention and control measures.

The scope of the document encompasses post harvest handling and storage measures for aflatoxin abatement in cereals, root crops, tree and oil crops and beverages. The document also contains guidelines for disposal of agricultural products that are highly contaminated with aflatoxin.  The above categories of crops were selected based on a criteria agreed upon by experts from the Partner States.  Under each category, key crops were selected and ranked on a scale of 1-5 based on the following attributes and parameters.

- Importance of the crop as a staple/ vital food security crop;

- Economic and industrial importance of the crop for feed and processing;

- Importance of the crop in intra and inter-regional trade;

- Popularity of crops widely grown by majority of farmers; and

- Degree of susceptibility to aflatoxin contamination.

Based on the above criteria, the following crops were selected:

- Cereal crops (maize, sorghum, rice, wheat, millet, and barley);

- Root crops (cassava);

- Tree and oil crops (ground nuts, cotton, soybean, cashew nut,

macadamia, sunflower and simsim); and

- Beverages (coffee).

Leading institutions for collecting the data: Ministry of Health: Directorate of Planning and Information Unit, Ministry of Trade: Directorate of Trade and FSQA, Ministry of Agriculture: Department of Agriculture (Extension Services) and National Agriculture Research Institute (NARI), National Nutrition Agency (NaNA), Medical Research Council

Contact person – Lamine Senghor

E.G. MDTF 2

These Roundtable discussions will be joint missions between AUC, NEPAD, RECs and country Officials in Health, Trade and Agriculture sector. Where , AUC will also be represented by the three sectors

TORs for the consultants will be reviewed and accepted by countries, countries will to help identify consultants. Consultants will engage all necessary stakeholder with the direct leadership of the CAADP Focal Point, consultants will also propose gaps in the NAFSIP that need to be strengthened in terms of Food Safety and specifically aflatoxin mitigation

Local Consultant will convene all stakeholders and based on inputs from the situation analysis, propose intervention areas to be included in the NAFSIP.  Stakeholders will then agree on priority intervention areas using tools available to be mainstreamed into the NAFSIP.

The Malawi Programme for Aflatoxin Control (MAPAC) is a new initiative of Malawi which aims at improving the health and livelihood of its people by effectively managing and controlling aflatoxin in its staple crops such as maize and groundnuts. Through the use of research, introduction of good practices, development of testing capacities in laboratories, and pushing for good policies, MAPAC tries to develop Malawi’s capacity to effectively control and reduce aflatoxin contamination in the key value chains. MAPAC was developed in alignment with the PACA Strategy

To read more about MAPAC, visit: http://www.standardsfacility.org/Files/Project_documents/Project_Preparation_Grants/STDF_PPG_400_FinalReport_Sep-13.pdfand http://www.aflatoxinpartnership.org/?q=node/132

using template submitted by country before workshop

Using template provided

Using reporting template to be provided by PACA Secretariat

E.G. MDTF 2

List all equipment available for sampling and sample preparation as well as for actual aflatoxin detection and measurement